## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Beldanga - II | Central Drilling | SHUKUR PUKUR PWSS | SM/16782 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2 | MURSHIDABAD | Beldanga - II | Berhampore Division I | SHUKUR PUKUR PWSS | SM/16782 | New | SHUKUR PUKUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Beldanga-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-II | JE_RAJIB BISWAS | ORD/000087/2023-2024 | 207/BD-I | 17/05/2023 | 15/08/2023 | ABIDA CONSTRUCTION | 40.82 | 0 | 0 | 0
3 | MURSHIDABAD | Beldanga - II | Berhampore Division I | SHUKUR PUKUR PWSS | SM/16782 | New | SHUKUR PUKUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-II | JE_RAJIB BISWAS | ORD/000133/2023-2024 | 612/BD-I | 02/08/2023 | 29/01/2024 | NOVELTY CONSTRUCTION | 52.15 | 0 | 0 | 20
4 | MURSHIDABAD | Beldanga - II | Berhampore Division I | SHUKUR PUKUR PWSS | SM/16782 | New | Material Requisition To Resource Division |  |  | RTOR000047/2023-2024 | 61/BD-1/34 | 27/04/2023 |  | Resource Division | 8.65 | 0 | 0 | 0
5 | MURSHIDABAD | Beldanga - II | Berhampore Mechanical | SHUKUR PUKUR PWSS | SM/16782 | New | NEW CONNECTION AT SUKURPUKUR PH-1 |  |  | BILL/00616/2024-2025 | null | 02/08/2024 |  | WBSEDCL | 10.55 | 0 | 0 | 0
Total | [13 empty] | 21451.93 | 0 | 0