## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bhagawangola - II | Central Drilling | PURBA GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/16783 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) |  |  | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 08/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 0 | 0 | 10
2 | MURSHIDABAD | Bhagawangola - II | Berhampore Division I | PURBA GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/16783 | New | PURBA GOBINDAPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000095/2023-2024 | 217/BD-I | 17/05/2023 | 15/08/2023 | SUPTI ENTERPRISE | 40.92 | 7.25 | 17.71 | 50
3 | MURSHIDABAD | Bhagawangola - II | Berhampore Division I | PURBA GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/16783 | New | PURBA GOBINDAPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 200 cum) under Jal Jivan Mission of BHAGWANGOLA -II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000246/2023-2024 | 967/BD-I | 17/10/2023 | 23/07/2024 | SAMBHUNATH ROY | 298.57 | 0 | 0 | 0
4 | MURSHIDABAD | Bhagawangola - II | Berhampore Division I | PURBA GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/16783 | New | Material Requisition To Resource Division |  |  | RTOR000041/2023-2024 | 61/BD-1/33 | 27/04/2023 |  | Resource Division | 13.12 | 0 | 0 | 0
5 | MURSHIDABAD | Bhagawangola - II | Berhampore Mechanical | PURBA GOBINDAPUR AND ADJOINING MOUJAS PWSS | SM/16783 | New | NEW CONNECTION AT PURBA GOBINDAPUR PH-1 |  |  | BILL/00243/2024-2025 | 102/WBSEDCL-JJM | 05/06/2024 |  | WBSEDCL | 6.06 | 0 | 0 | 0
Total | [13 empty] | 1078.91 | 7.25 | 0.67