## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Lalgola | Central Drilling | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) |  |  | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 08/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 0 | 0 | 10
2 | MURSHIDABAD | Lalgola | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | BAYRA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | Assistant Engineer-I |  | ORD/000118/2023-2024 | 512/BD-I | 25/07/2023 | 21/01/2024 | SRIJON ENTERPRISE | 244.14 | 0 | 0 | 0
3 | MURSHIDABAD | Lalgola | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | BAYRA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer,Assistant Engineer-I | JE | ORD/000137/2023-2024 | 620/BD-I | 03/08/2023 | 30/01/2024 | RAJEN DAS | 55.72 | 0 | 0 | 50
4 | MURSHIDABAD | Lalgola | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | BAYRA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | Assistant Engineer-I |  | ORD/000147/2023-2024 | 634/BD-I | 04/08/2023 | 03/08/2024 | M/S GHOSH AND CO | 383.82 | 0 | 0 | 0
5 | MURSHIDABAD | Lalgola | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | BAYRA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte.. | Assistant Engineer | JE | ORD/000341/2023-2024 | 1255/BD-I | 22/12/2023 | 21/03/2024 | MASOOM TRADERS | 61.36 | 0 | 0 | 0
6 | MURSHIDABAD | Lalgola | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | Material Requisition To Resource Division |  |  | RTOR000097/2023-2024 | 201/BD-1/26 | 10/02/2024 |  | Resource Division | 39.6 | 0 | 0 | 0
7 | MURSHIDABAD | Lalgola | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | Material Requisition To Resource Division |  |  | RTOR000109/2023-2024 | 304/BD-1/6 | 22/02/2024 |  | Resource Division | 24.04 | 0 | 0 | 0
8 | MURSHIDABAD | Lalgola | Berhampore Mechanical | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | NEW CONNECTION BAYRA PH-1 |  |  | BILL/01513/2023-2024 | 388/WBSEDCL-JJM | 04/03/2024 |  | WBSEDCL | 6.05 | 0 | 0 | 0
9 | MURSHIDABAD | Lalgola | Berhampore Mechanical | BAYRA AND ITS ADJOINING MOUJAS PWSS | SM/18414 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under BAYRA ground water based water supply scheme under Block_LALGOLA Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/001433/2023-2024 | 4313/MEDB | 29/12/2023 | 28/03/2024 | HARA PROSAD DAS | 33.24 | 0 | 0 | 0
Total | [13 empty] | 1568.2 | 0 | 0