## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Bhagawangola - II | Berhampore Division I | NASIPUR AND ADJOINIONG MOUJAS PWSS | SM/18517 | New | NASIPUR PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | Assistant Engineer-I |  | ORD/000182/2023-2024 | 698/BD-I | 11/08/2023 | 07/02/2024 | JAHANGIR ALAM | 263.59 | 0 | 0 | 0
2 | MURSHIDABAD | Bhagawangola - II | Berhampore Division I | NASIPUR AND ADJOINIONG MOUJAS PWSS | SM/18517 | New | NASIPUR PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer-I |  | ORD/000183/2023-2024 | 701/BD-I | 11/08/2023 | 07/02/2024 | RAJ KUMAR MONDAL | 193.43 | 0 | 0 | 0
3 | MURSHIDABAD | Bhagawangola - II | Berhampore Division I | NASIPUR AND ADJOINIONG MOUJAS PWSS | SM/18517 | New | NASIPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 750 cum) under Jal Jeevan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000202/2023-2024 | 846/BD-I | 05/09/2023 | 11/07/2024 | JAHANGIR ALAM | 466.95 | 0 | 0 | 0
4 | MURSHIDABAD | Bhagawangola - II | Berhampore Division I | NASIPUR AND ADJOINIONG MOUJAS PWSS | SM/18517 | New | NASIPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000340/2023-2024 | 1254/BD-I | 22/12/2023 | 21/03/2024 | MASOOM TRADERS | 56.23 | 0 | 0 | 25
5 | MURSHIDABAD | Bhagawangola - II | Berhampore Division I | NASIPUR AND ADJOINIONG MOUJAS PWSS | SM/18517 | New | Material Requisition To Resource Division |  |  | RTOR000101/2023-2024 | 201/BD-1/5 | 10/02/2024 |  | Resource Division | 86.32 | 0 | 0 | 0
6 | MURSHIDABAD | Bhagawangola - II | Berhampore Mechanical | NASIPUR AND ADJOINIONG MOUJAS PWSS | SM/18517 | New | NEW CONNECTION NASIPUR PH-1 |  |  | BILL/01575/2023-2024 | 410/WBSEDCL-JJM | 06/03/2024 |  | WBSEDCL | 21.19 | 0 | 0 | 0
Total | [13 empty] | 1087.71 | 0 | 0