## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Beldanga - II | Central Drilling | GHOLLA AND ADJOINING MOUJAS PWSS | SM/18581 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 7.03 | 0.03 | 11
2 | MURSHIDABAD | Beldanga - II | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS | SM/18581 | New | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Gholla" ground water supply scheme in Beldanga-II Block, under Berhampore Division-I, P.H.E Dte. (Capacity-119 Cum/hr.) Type-1 - Fully Gravity System with RG Filter | Assistant Engineer-II |  | ORD/000035/2024-2025 | 999/BD-I | 20/06/2024 | 20/06/2025 | M/S GOUTAM CHAKRABORTY | 272.44 | 0 | 0 | 0
3 | MURSHIDABAD | Beldanga - II | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS | SM/18581 | New | GHOLLA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Beldanga-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-II | JE | ORD/000150/2023-2024 | 660/BD-I | 08/08/2023 | 06/11/2023 | GITA CONSTRUCTION | 69.92 | 0 | 0 | 0
4 | MURSHIDABAD | Beldanga - II | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS | SM/18581 | New | GHOLLA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | Assistant Engineer-II |  | ORD/000163/2023-2024 | 648/BD-I | 08/08/2023 | 04/02/2024 | HARAPRASAD DAS | 118.61 | 0 | 0 | 0
5 | MURSHIDABAD | Beldanga - II | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS | SM/18581 | New | GHOLLA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | Assistant Engineer-II |  | ORD/000164/2023-2024 | 647/BD-I | 08/08/2023 | 04/02/2024 | M/S JHA CONSTRUCTION | 180.62 | 0 | 0 | 0
6 | MURSHIDABAD | Beldanga - II | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS | SM/18581 | New | GHOLLA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE Dte. (PART A) | Assistant Engineer-II |  | ORD/000165/2023-2024 | 649/BD-I | 08/08/2023 | 07/08/2024 | RAJ KUMAR MONDAL | 404.58 | 0 | 0 | 2
7 | MURSHIDABAD | Beldanga - II | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS | SM/18581 | New | Fabrication and errection of Display Board including vinyl pasting ( 1.80 x 1.20 mtr) of scheme information by using logo and tag line of Jal Jevan Mission at different work sites in the district of Murshidabad under Berhampore Division-I,PHE Dte. | Assistant Engineer-I | Junior Engineer | ORD/000446/2023-2024 | 446/BD-I | 15/03/2024 | 04/04/2024 | SUMAN ENTERPRISE AND SUMAN AQUA | 7.18 | 3.35 | 46.58 | 100
8 | MURSHIDABAD | Beldanga - II | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS | SM/18581 | New | Material Requisition To Resource Division |  |  | RTOR000102/2023-2024 | 201/BD-1/1 | 10/02/2024 |  | Resource Division | 25 | 0 | 0 | 0
9 | MURSHIDABAD | Beldanga - II | Berhampore Mechanical | GHOLLA AND ADJOINING MOUJAS PWSS | SM/18581 | New | NEW CONNECTION AT GHOLLA PH-I |  |  | BILL/00172/2024-2025 | 14/WBSEDCL-JJM | 16/04/2024 |  | WBSEDCL | 5.35 | 0 | 0 | 0
Total | [13 empty] | 22423.48 | 10.37 | 0.05