## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Aligarh PWSS (Phase-I) | SM/06733 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Gangmuri, of Aligarh w/s Scheme at Suri-I Block under Birbhum Division, PHE Dte. (Sl. No.2) | AE | JE3 | ORD/000065/2020-2021 | 1237 /BHM | 28/09/2020 | 12/11/2020 | S R ENTERPRISE | 21.49 | 20.65 | 96.1 | 0
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Aligarh PWSS (Phase-I) | SM/06733 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Madanpur, Jaypur, Talpur, Rahida, Ranigram, Hirapur, Marbuni, Laubani) of Aligarh w/s Scheme at Suri-I Block under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000067/2020-2021 | 1167 /BHM | 21/09/2020 | 20/11/2020 | M/S KRIPASINDHU GHOSH & CO. | 42.21 | 42.16 | 99.89 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Aligarh PWSS (Phase-I) | SM/06733 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Sahabad, Azimnagar, Natangram, Gobra of Aligarh w/s Scheme at Suri-I Block under Birbhum Division, PHE Dte. (Sl. No.1) | AE | JE3 | ORD/000219/2020-2021 | 1236 /BHM | 28/09/2020 | 12/11/2020 | RAJ KUMAR DAS | 25.65 | 4.41 | 17.19 | 40
Total | [13 empty] | 89.35 | 67.23 | 75.24