## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) | SM/06740 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Batikar Gram Panchayet under Batikar Water Supply Scheme in Batikar Jagpalla and Batikar Bus Stand and Repairing of pipeline due to leakage of house connection in distributions pipeline in different area (i.e. Kustikuri, Nabagram and Charakdanga) under Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.: 02). | AE | JE1 | ORD/000055/2022-2023 | 201/BSD | 20/05/2022 | 19/06/2022 | M/S SARADA CONSTRUCTION. | 3.98 | 3.02 | 75.75 | 75
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) | SM/06740 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at habitation Batikor, village-Batikor (JL No.02) at different locations from existing distribution system within the command area of Batikor piped water supply scheme at Illambazar Block under Bolpur Sub Division within Birbhum Division, PHE Dte. (Phase-1) | AE | JE4 | ORD/000079/2020-2021 | 1089/BHM | 05/09/2020 | 05/10/2020 | PRANAB KUMAR GHOSH | 4.71 | 4.71 | 100 | 0
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) | SM/06740 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Narasonda, Ikshusara, Anaipur of Batikar w/s Scheme at Illambazar Block under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE | JE4 | ORD/000080/2020-2021 | 1171 /BHM | 21/09/2020 | 20/11/2020 | MS B N ENTERPRISES | 39.49 | 22.6 | 57.23 | 0
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) | SM/06740 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Batikor of Batikar w/s Scheme at Illambazar Block under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE | JE4 | ORD/000081/2020-2021 | 1170 /BHM | 21/09/2020 | 20/11/2020 | HIMANGSU SEKHAR SARKAR | 31.27 | 23.66 | 75.67 | 0
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) | SM/06740 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Khushtikuri of Batikar w/s Scheme at Illambazar Block under Bolpur Sub-Division within Birbhum Division, PHE Dte. (6a) |  | JE4 | ORD/000082/2020-2021 | 1172 /BHM | 21/09/2020 | 05/11/2020 | INDRAJIT DAS | 24.28 | 18.41 | 75.84 | 89
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) | SM/06740 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Narasonda, Ikshusara, Anaipur of Batikar w/s Scheme at Illambazar Block under Bolpur Sub-Division within Birbhum Division, PHE Dte | AE | JE4 | ORD/000211/2020-2021 | 1563/BHM | 17/12/2020 | 15/02/2021 | MS B N ENTERPRISES | 4.91 | 0 | 0 | 0
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) | SM/06740 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Karchadihi Mouza within the command area of for Batikar Water Supply Scheme under Bolpur Sub Division of Birbhum Division, PHE Dte.(Sl. No.2) | AE | JE4 | ORD/000280/2020-2021 | 255/BHM | 26/02/2021 | 12/04/2021 | MS KAZIMEHERUDDIN | 4.67 | 4.67 | 99.93 | 100
8 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) | SM/06740 | Retrofitting | Retrofitting work for Providing Balance Functional Household Tap Connection (FHTC) within the Command area of Batikar Water Supply Scheme in Anaipur (Purbo Para) village for Swajal Gram under Illambazar Block of Bolpur Sub-Division within Birbhum Division P.H.E. Deptt. | AE | JE1 | ORD/000299/2022-2023 | 381/BSD | 29/09/2022 | 09/10/2022 | M/S SARADA CONSTRUCTION. | 0.96 | 0.82 | 84.84 | 91
9 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) | SM/06740 | Retrofitting | Retrofitting work for Providing Balance Functional Household Tap Connection (FHTC) within the Command area of Batikar Water Supply Scheme in Karchadihi, Ikshusara and Anaipur (Paschim Para) village for Swajal Gram under Illambazar Block of Bolpur Sub-Division within Birbhum Division P.H.E. Deptt. | AE | JE1 | ORD/000300/2022-2023 | 382/BSD | 29/09/2022 | 09/10/2022 | M/S SARADA CONSTRUCTION. | 0.97 | 0.86 | 89.27 | 91
10 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) | SM/06740 | Retrofitting | Providing Functional Household Tap Connection (FHTC) for remaining household at UTTAR SULTANPUR Mouza from existing distribution System within the command area of Batikar Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. | AE | JE4 | ORD/000349/2021-2022 | 403/BSD | 25/10/2021 | 04/11/2021 | INDRAJIT DAS | 0.96 | 0.6 | 62.5 | 100
11 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) | SM/06740 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Balta Mouza (Part) within the command area of Batikar Water Supply Scheme under Bolpur Sub Division of Birbhum Division, PHE Dte. (Sl. No.1) | AE | JE4 | ORD/000492/2020-2021 | 280/BHM | 26/02/2021 | 12/04/2021 | HIMANGSU SEKHAR SARKAR | 4.67 | 4.5 | 96.47 | 100
12 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) | SM/06740 | Retrofitting | Retrofitting work for Providing Balance Functional Household Tap Connection (FHTC) in Batikar (02) under BATIKAR Gram Panchayat within the Command area of Batikar Water Supply, Scheme for Swajal Gram under Illambazar Block of Bolpur Sub-Division within BIRBHUM DIVISION P.H.E. Deptt.(Sl. No.12) | AE | JE1 | ORD/000500/2022-2023 | 332/BHM | 02/02/2023 | 19/03/2023 | KAUSHIK RAY | 18.74 | 0 | 0 | 100
13 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) | SM/06740 | Retrofitting | Construction of remaining Boundary Wall at Head Work site of BATIKAR Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Length: 123 Mtr.). (Sl. 04) | AE | JE1 | ORD/000736/2021-2022 | 425/BSD | 18/11/2021 | 17/01/2022 | GANAPATI ENGINEERING CORP. | 4.85 | 0 | 0 | 0
14 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) | SM/06740 | Retrofitting | Balance work of Laying Rising main with inter connection pipe line from Tube Well No. - 2 to Tube Well No. - 1 including OHR with Distribution main of BATIKAR Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Sl. No. -10) | AE | JE4 | ORD/000803/2021-2022 | 320/BSD | 31/08/2021 | 15/09/2021 | PRANAB KUMAR GHOSH | 0.93 | 0 | 0 | 0
15 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) | SM/06740 | Retrofitting | Allied works of extension boosting pipe lines for Providing Functional Household Tap Connection (FHTC) from existing distribution system in various node point (From 03 to 11,110 to 120, 144 to 158, 9 to 168 174 to 175), of Batikar village within the command area in the villages Batikar (JL No.- 02.) Water Supply Scheme at Illambazar Block under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. - 03) | AE | JE1 | ORD/000830/2021-2022 | 11/BSD | 11/01/2022 | 10/02/2022 | HIMANGSU SEKHAR SARKAR | 4.38 | 4.26 | 97.35 | 100
16 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) | SM/06740 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing Distribution System within the command area of Batikar Water Supply Scheme at Mouja: KHUSTIKURI & UTTAR SULTANPUR under Bolpur Sub Division within Birbhum Division, PHED. (Sl. - 01) | AE | JE4 | ORD/000844/2021-2022 | 379/ BSD | 07/10/2021 | 06/11/2021 | MS KAZIMEHERUDDIN | 4.77 | 4.77 | 99.99 | 100
17 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) | SM/06740 | Retrofitting | Retrofitting works to the existing distribution system within the command area of Batikar Water Supply Scheme at Khustikuri and Narasonda Moujas under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE | JE4 | ORD/001074/2021-2022 | 324/BSD | 01/09/2021 | 01/10/2021 | INDRAJIT DAS | 4.85 | 2.75 | 56.69 | 74
Total | [13 empty] | 159.38 | 95.63 | 60