## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works of Narayanghati under Mayureswar-II Block PWSS for providing Functional Household Tap Connection (FHTC) within the command area | SM/06950 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Narayanghati w/s Scheme in Rampurhat Sub-Division under Birbhum Division, PHE Dte. (Sl. No.-2) | AE | JE1 | ORD/000548/2021-2022 | 1915 /BHM | 24/11/2021 | 23/01/2022 | TAPAN KUMAR DATTA | 82.11 | 78.79 | 95.96 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works of Narayanghati under Mayureswar-II Block PWSS for providing Functional Household Tap Connection (FHTC) within the command area | SM/06950 | Retrofitting | Laying of HDPE Pipe line for Induripara at Balur mouza for providing FHTC under Narayanghati Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000680/2021-2022 | 122/RSD | 11/03/2022 | 10/04/2022 | TAPAN KUMAR DATTA | 4.94 | 9.02 | 182.56 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works of Narayanghati under Mayureswar-II Block PWSS for providing Functional Household Tap Connection (FHTC) within the command area | SM/06950 | Retrofitting | Laying of HDPE Pipe line for Akna, Balur, Nima dangal at diff mouzas for providing FHTC under Narayanghati Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000681/2021-2022 | 123/RSD | 11/03/2022 | 10/04/2022 | TAPAN KUMAR DATTA | 4.93 | 0 | 0 | 0
4 | BIRBHUM |  | Birbhum Division | Retrofitting works of Narayanghati under Mayureswar-II Block PWSS for providing Functional Household Tap Connection (FHTC) within the command area | SM/06950 | Retrofitting | Laying of HDPE Pipe line for Kalikapur, Mahalas at Kalikapur mouza for providing FHTC under Narayanghati Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000682/2021-2022 | 124/RSD | 11/03/2022 | 10/04/2022 | TAPAN KUMAR DATTA | 4.96 | 4.45 | 89.77 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works of Narayanghati under Mayureswar-II Block PWSS for providing Functional Household Tap Connection (FHTC) within the command area | SM/06950 | Retrofitting | Laying of HDPE Pipe line for Narayanghati mouza for providing FHTC under Narayanghati Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000683/2021-2022 | 125/RSD | 11/03/2022 | 10/04/2022 | TAPAN KUMAR DATTA | 4.98 | 4.66 | 93.53 | 100
Total | [13 empty] | 101.92 | 96.92 | 95.09