## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bansjore PWSS (Phase-I) | SM/07006 | Retrofitting | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bansjore W/S Scheme in Suri Sadar Sub-Division under Birbhum Division, PHE Dte. | AE | JE1 | ORD/000053/2023-2024 | 1248/BHM | 17/04/2023 | 01/06/2023 | PRANAB KUMAR GHOSH | 33.15 | 32.75 | 98.8 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bansjore PWSS (Phase-I) | SM/07006 | Retrofitting | Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bansjore W/S Scheme in Suri Sadar Sub-Division under Birbhum Division, P.H.E. Dte. (Sl. No.- 2) | AE | JE1 | ORD/000355/2021-2022 | 1865/BHM | 16/11/2021 | 15/01/2022 | PRANAB KUMAR GHOSH | 65.87 | 20.25 | 30.75 | 45
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bansjore PWSS (Phase-I) | SM/07006 | Retrofitting | Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bansjore w/s Scheme in Suri Sadar Sub-Division under Birbhum Division, PHE Dte.¿(Sl. No.2) | AE | JE1 | ORD/000570/2021-2022 | 1865/ BHM | 16/11/2021 | 15/01/2022 | PRANAB KUMAR GHOSH | 65.87 | 41.5 | 63.01 | 85
Total | [13 empty] | 164.89 | 94.51 | 57.32