## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum | SM/07531 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Jhaupara, Dattakaya, Shingdohari in Haridaspur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte (Sl. No.9) | AE | JE1 | ORD/000001/2021-2022 | 681/BHM | 01/06/2021 | 31/07/2021 | BELAL SK | 43.79 | 77.21 | 176.33 | 92
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum | SM/07531 | Retrofitting | Sinking and replacement of 200mm dia 60 m. deep tubewell fitted with PVC pipe and fibre glass Strainer at Haridaspur (near head work side) PWSS under Nalhati Sub-Division within Birbhum Division,PHE Dte. | AE | JE1 | ORD/000002/2022-2023 | 208/AE/NSD | 05/04/2022 | 05/05/2022 | SURJASISH DATTA | 3.74 | 0 | 0 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum | SM/07531 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Haridaspur in Haridaspur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.10) | AE | JE1 | ORD/000003/2021-2022 | 1006/BHM | 11/06/2021 | 10/08/2021 | M/S KRIPASINDHU GHOSH & CO. | 36.62 | 73.22 | 199.96 | 100
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum | SM/07531 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Bhagabatipur in Haridaspur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.12) | AE | JE1 | ORD/000004/2021-2022 | 1015/BHM | 15/06/2021 | 14/08/2021 | TAPAN KUMAR DATTA | 30.21 | 30.21 | 100 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum | SM/07531 | Retrofitting | Construction of Boundary Wall at OHR site at Haridaspur Piped Water Supply Scheme (South side) under Nalhati Sub-Division within Birbhum Division, PHED. | AE | JE1 | ORD/000009/2022-2023 | 224/AE/NSD | 19/04/2022 | 18/06/2022 | RAJA CONSTRUCTION | 4.84 | 0 | 0 | 45
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum | SM/07531 | Retrofitting | Balance work for construction of High Lift Pump house including stainless steel railing at Haridaspur PWSS Under Nalhati Sub Division within Birbhum Division, P.H.E. Dte. | AE | JE1 | ORD/000106/2022-2023 | 357/AE/NSD | 20/07/2022 | 03/09/2022 | SUNIL RABI DAS | 5 | 0 | 0 | 0
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum | SM/07531 | Retrofitting | Extention of pipeline by HDPE pipe at Gunia and Kalyanpur habitation for providing FHTC of Haridaspur Water Supply Scheme under Nalhati Sub-Division within Birbhum Division PHED. | AE | JE1 | ORD/000112/2022-2023 | 200/AE/NSD | 01/04/2022 | 16/05/2022 | M/S S.N CONSTRUCTION | 3.15 | 2.44 | 77.44 | 100
8 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum | SM/07531 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Sanakpur in Haridaspur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.8) | AE | JE1 | ORD/000130/2021-2022 | 910/BHM | 10/06/2021 | 09/08/2021 | MS B N ENTERPRISES | 32.66 | 32.22 | 98.63 | 100
9 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum | SM/07531 | Retrofitting | Extention of pipeline by HDPE pipe at Bhagabatipur and Chachka habitations for providing FHTC of Haridaspur Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHED. | AE | JE1 | ORD/000152/2022-2023 | 211/AE/NSD | 07/04/2022 | 22/05/2022 | HUMAYUN KABIR | 4.84 | 0 | 0 | 100
10 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum | SM/07531 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Chachka-Balarampur habitations under Haridaspur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000309/2021-2022 | 530/AE/NSD | 08/10/2021 | 22/11/2021 | SUBHRANIL DAS | 4.74 | 4.74 | 100 | 100
11 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum | SM/07531 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Chachka habitations under Haridaspur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000310/2021-2022 | 531/AE/NSD | 08/10/2021 | 22/11/2021 | HUMAYUN KABIR | 4.75 | 4.75 | 100 | 100
12 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum | SM/07531 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Jungul,Gunua in Haridaspur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.11) | AE | JE1 | ORD/000330/2020-2021 | 274 / BHM | 26/02/2021 | 12/04/2021 | KAZI EMDADUL HAQUE | 23.6 | 42.08 | 178.31 | 95
13 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum | SM/07531 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Kalyanpur Habitation under Haridaspur W/S Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000360/2021-2022 | 593/AE/NSD | 23/11/2021 | 07/01/2022 | M/S S.N CONSTRUCTION | 4.82 | 4.81 | 99.97 | 100
14 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum | SM/07531 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Gunia Habitation under Haridaspur W/S Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000361/2021-2022 | 594/AE/NSD | 23/11/2021 | 07/01/2022 | AJIMUL ISLAM | 4.82 | 4.82 | 99.97 | 100
15 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum | SM/07531 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Dasturpur (South) Habitation under Haridaspur W/S Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000362/2021-2022 | 595/AE/NSD | 23/11/2021 | 07/01/2022 | DATA CONSTRUCTION | 4.82 | 4.82 | 99.97 | 100
16 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum | SM/07531 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Dasturpur (North) Habitation under Haridaspur W/S Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000363/2021-2022 | 596/AE/NSD | 23/11/2021 | 07/01/2022 | SURJASISH DATTA | 4.82 | 0 | 0 | 100
17 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum | SM/07531 | Retrofitting | Sinking of 200mm 50 m. deep replacement (No.-1) Tube well fitted with 200 mm dia. PVC pipe and fibre glass Strainer etc. all complete at Haridaspur Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE1 | ORD/000611/2021-2022 | 122/AE/NSD | 04/03/2022 | 03/04/2022 | SURJASISH DATTA | 3.3 | 0 | 0 | 100
18 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum | SM/07531 | Retrofitting | Land development including strengthening of River side filling HARIDASPUR PWSS under Nalhati Sub-Division, PHE Dte. | AE | JE1 | ORD/000623/2021-2022 | 22/NSD | 17/01/2022 | 07/02/2022 | SUNIL RABI DAS | 4.84 | 0 | 0 | 100
Total | [13 empty] | 225.34 | 281.31 | 124.84