## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. | SM/08893 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Amdole under Amdole Water Supply Scheme (Left out House Hold) within Birbhum Division, PHE Dte. (Sl. No.11) | AE | JE3 | ORD/000039/2022-2023 | 885/BHM | 22/04/2022 | 21/06/2022 | KHANDAKAR CONSTRUCTION | 66.42 | 66.11 | 99.53 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. | SM/08893 | Retrofitting | ¿Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Amdole Water Supply Scheme within Nalhati Sub-Division under Birbhum Division, PHE Dte.¿(Sl. No.17) | AE | JE2 | ORD/000340/2021-2022 | 1771/BHM | 29/10/2021 | 28/12/2021 | UJJWAL DAS | 78.86 | 78.86 | 100 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. | SM/08893 | Retrofitting | Extension of pipeline of different left out habitations including FHTC along with 1 no. Pump House as boosting of water supply of Amdol water supply scheme under Nalhati Sub-Division, within Birbhum Division PHE Dte (Sl. No.7) | AE | JE3 | ORD/000367/2022-2023 | 2780/BHM | 14/12/2022 | 27/02/2023 | KAMIRUL SK AND CO | 211.6 | 45.93 | 21.7 | 75
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. | SM/08893 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Amdole w/s Scheme (Leftout House Hold) in Nalhati Sub-Division under Birbhum Division, PHE Dte. (Sl. No.5) | AE | JE2 | ORD/000415/2021-2022 | 2098/BHM | 16/12/2021 | 14/02/2022 | MD ABSAR ALI | 94.06 | 94.06 | 100 | 100
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. | SM/08893 | Retrofitting | Restoration of PCC Road, damaged by laying of pipe line at different habitations under Narottampur village (JL.No.-63) and its adjoining areas under Amdol PWSS within Nalhati Sub-Division, PHE Dte. | AE | JE2 | ORD/000625/2021-2022 | 539/AE/NSD | 08/10/2021 | 23/10/2021 | TEKNO ENTERPRISE | 4.46 | 0 | 0 | 100
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. | SM/08893 | Retrofitting | Restoration of PCC Road, damaged by laying of pipe line at different habitations under Kalahapur village (JL.No.-56) and its adjoining areas under Amdol PWSS within Nalhati Sub-Division, PHE Dte. | AE | JE2 | ORD/000626/2021-2022 | 534/AE/NSD | 08/10/2021 | 23/10/2021 | MD ABSAR ALI | 4.85 | 0 | 0 | 100
7 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. | SM/08893 | Retrofitting | Road crossing under Kalahapur village by adopting Augor Boring method along with pipe carrying structure & other ancillary works for Improvement of AMDOL PWSS under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000628/2021-2022 | 19/AE/NSD | 17/01/2022 | 16/02/2022 | MD ABSAR ALI | 4.85 | 0 | 0 | 100
8 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. | SM/08893 | Retrofitting | Road crossing near Bhimpur Health Center by adopting Jack Pushing method for Improvement of AMDOL PWSS under Nalhati Sub-Division within Birbhum Division, PHE Dte. | AE | JE2 | ORD/000629/2021-2022 | 20/NSD | 17/01/2022 | 16/02/2022 | UJJWAL DAS | 4.84 | 0 | 0 | 100
9 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. | SM/08893 | Retrofitting | Extension of pipe line at Kalahapur village of Amdol Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. | AE | JE2 | ORD/000637/2021-2022 | 490/AE/NSD | 27/09/2021 | 11/11/2021 | MD ABSAR ALI | 4.52 | 0 | 0 | 100
10 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. | SM/08893 | Retrofitting | Restoration of PCC Road, damaged by laying of pipe line at different habitations under Hariapur village (JL.No.-60) and its adjoining areas under Amdol PWSS within Nalhati Sub-Division, PHE Dte. | AE | JE2 | ORD/000782/2021-2022 | 536/AE/NSD | 08/10/2021 | 23/10/2021 | UJJWAL DAS | 4.84 | 0 | 0 | 100
11 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. | SM/08893 | Retrofitting | Laying of additional distribution system at Harishpur (JL.No.-60) and its adjoining areas for proposed Improvement of Amdol Piped Water Supply Scheme under Murarai-II Block, under Birbhum Division, PHE Dte. | AE | JE2 | ORD/000785/2021-2022 | 536/A/AE/NSD | 08/10/2021 | 22/11/2021 | UJJWAL DAS | 4.98 | 0 | 0 | 0
Total | [13 empty] | 484.29 | 284.96 | 58.84