## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BISHNUPUR (PHASE-II) WATER SUPPLY SCHEME of Rampurhat-II Block under Birbhum Division, PHE Dte. | SM/08896 | Retrofitting | Distribution System including providing Functional Household Tap Connection(FHTC) at Lalitakundu Paschim Par within the command area of Bishnupur Water Supply Scheme Under RWS Birbhum Sub-Division,within Birbhum Division,PHE Dte.(Sl. No.07) | AE | JE3 | ORD/000081/2022-2023 | 136/BH | 15/06/2022 | 15/07/2022 | BIJOY KUMAR CHOUDHURY | 4.71 | 4.69 | 99.57 | 50
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BISHNUPUR (PHASE-II) WATER SUPPLY SCHEME of Rampurhat-II Block under Birbhum Division, PHE Dte. | SM/08896 | Retrofitting | Providing Functional Household Tap Connection(FHTC) at Lalitakundu Purba Par within the command area of Bishnupur Water Supply Scheme under RWS Birbhum Sub-Division within Birbhum Division, PHE Dte. (Sl. No.08) | AE | JE | ORD/000087/2022-2023 | 137/BH | 15/06/2022 | 05/07/2022 | BIJOY KUMAR CHOUDHURY | 3.56 | 3.54 | 99.43 | 100
3 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BISHNUPUR (PHASE-II) WATER SUPPLY SCHEME of Rampurhat-II Block under Birbhum Division, PHE Dte. | SM/08896 | Retrofitting | Providing Functional Household Tap Connection(FHTC) at Baswa Lat Para within the command area of Bishnupur Water Supply Scheme under RWS Birbhum Sub-Divition within Birbhum Division PHE Dte.(Sl. No.09) | AE | JE3 | ORD/000088/2022-2023 | 138/BH | 15/06/2022 | 05/07/2022 | BIJOY KUMAR CHOUDHURY | 3.6 | 3.58 | 99.53 | 50
4 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BISHNUPUR (PHASE-II) WATER SUPPLY SCHEME of Rampurhat-II Block under Birbhum Division, PHE Dte. | SM/08896 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Baroipara and its adjoining area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | AE | JE | ORD/000364/2021-2022 | 177/BH | 03/11/2021 | 18/11/2021 | TAPAN ENTERPRISE | 4.83 | 0 | 0 | 50
5 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BISHNUPUR (PHASE-II) WATER SUPPLY SCHEME of Rampurhat-II Block under Birbhum Division, PHE Dte. | SM/08896 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bishnupur Water Supply Scheme within Rampurhat Sub-Division under Birbhum Division, PHE Dte¿ (Sl. No.2) | AE | JE | ORD/000664/2021-2022 | 2033/ BHM | 09/12/2021 | 07/02/2022 | TAPAN KUMAR DATTA | 94.18 | 67.27 | 71.43 | 40
6 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BISHNUPUR (PHASE-II) WATER SUPPLY SCHEME of Rampurhat-II Block under Birbhum Division, PHE Dte. | SM/08896 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000040/2021-2022 | 218/BHM | 02/02/2022 |  | Resource Division | 26.49 | 0 | 0 | 0
Total | [13 empty] | 137.38 | 79.09 | 57.57