## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Hajrapur PWSS within Dubrajpur Block District Birbhum under Birbhum Division, PHE Dte. | SM/09369 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Hajarpur under Hajarpur Water Supply Scheme within Birbhum Division, PHE Dte.¿ (Sl. No.10) | AE |  | ORD/000149/2022-2023 | 1453/BHM | 07/07/2022 | 05/09/2022 | SAPTADIP CONSTRUCTION | 25.25 | 25.18 | 99.73 | 100
2 | BIRBHUM |  | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Hajrapur PWSS within Dubrajpur Block District Birbhum under Birbhum Division, PHE Dte. | SM/09369 | Retrofitting | Construction of 300 Cum capacity and 20.0m staging height RCC Over Head Reservoir & Laying distribution system including all allied works as per departmental drawing (DRG. No. PC-I/OHR/07/2012) for Hajrapur Piped Water Supply Scheme under Dubrajpur Block under Birbhum Sadar Sub-Division, PHE Dte. within Birbhum Division, PHE Dte (Sl. No.7) | AE | Estimator,JE3 | ORD/000827/2021-2022 | 1196/BHM | 07/12/2021 | 19/12/2021 | PASCON | 204.74 | 0 | 0 | 92
Total | [13 empty] | 229.99 | 25.18 | 10.95