## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Repairing and renovation of the Boundary Wall of Labpur Zone-II Water Supply Scheme at Laghata under RWS, Birbhum Sub-Division, PHE Dte. within Birbhum Division, PHE Dte. Suri, Birbhum(Phase-I) Sl.No.-1. | AE | JE1,JE2,Bolpur Sub-Division,JE3 | ORD/000095/2022-2023 | 130/BH | 15/06/2022 | 30/07/2022 | SOURAV MONDAL | 4.23 | 0 | 0 | 0
2 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Laying distribution system with FHTC for proposed augmentation scheme for Illambazar Piped Water Supply Scheme, Illambazar Block, under Birbhum Division, PHE Dte | Assistant Engineer | JE1 ,JE3 | ORD/000095/2024-2025 | 2113/BHM | 29/07/2024 | 27/10/2024 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 625.69 | 0 | 0 | 0
3 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Construction of 900cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC pile foundation including pipe connection & allied works for augmentation of Illmbazar W/S Scheme under Birbhum Division, PHE Dte.(As per Departmental Drawing)? (Sl. No.2) | AE | JE1,JE2,Bolpur Sub-Division,JE3 | ORD/000237/2022-2023 | 20003/BHM | 22/09/2022 | 19/06/2023 | APURBA MONDAL | 185.75 | 0 | 0 | 0
4 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Construction of 750cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC pile foundation including pipe connection & allied works for augmentation of Kirnahar Zone-I W/S Scheme under Birbhum Division, PHE Dte.(As per Departmental Drawing)¿ (Sl. No.8) | AE | JE3 | ORD/000241/2022-2023 | 2769/BHM | 14/12/2022 | 10/09/2023 | TEKNO ENTERPRISE | 165.61 | 136.63 | 82.5 | 97
5 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Construction of 750cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC pile foundation including pipe connection & allied works for augmentation of Chandidas W/S Scheme under Birbhum Division, PHE Dte.(As per Departmental Drawing) | AE | JE_BLK_NANOOR | ORD/000251/2022-2023 | 2592/BHM | 23/11/2022 | 20/08/2023 | CHIRANJIB DAS | 165.15 | 33.03 | 20 | 95
6 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Construction of 900cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC pile foundation including pipe connection & allied works for augmentation of Labhpur Zone-II W/S Scheme under Birbhum Division, PHE Dte. (As per Departmental Drawing) | AE | JE3 | ORD/000252/2022-2023 | 2466/BHM | 11/11/2022 | 08/08/2023 | SATYANARAYAN ENGINEER'S CO-OP.SOCIETY LTD. | 185.52 | 14.83 | 8 | 20
7 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Laying distribution system for proposed augmentation scheme for Labpur (Zone - I) Piped Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE | JE1,JE2,Bolpur Sub-Division,JE3 | ORD/000303/2022-2023 | 1028/BHM | 12/05/2022 | 08/11/2022 | ROY ENTERPRISE | 420.9 | 355.88 | 84.55 | 100
8 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Laying distribution system for proposed augmentation scheme for kirnahar (zone-I) piped water Supply Scheme under Nanoor Block, under Birbhum Division PHE Dte (Sl.No.5) | AE | JE1,JE2,Bolpur Sub-Division,JE3 | ORD/000310/2022-2023 | 804/BHM | 12/04/2022 | 09/10/2022 | TEKNO ENTERPRISE | 398.76 | 257.97 | 64.69 | 87
9 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Providing Balance Functional Tap Connection (FHTC) from existing distribution system within the command area for Augmentation of Joydev- Kendhuli Water Supply Scheme (For Swajal Gram) within Bolpur Sub - Division PHE Dte. | AE | JE1,JE2,Bolpur Sub-Division,JE3 | ORD/000313/2022-2023 | 2498/BHM | 17/11/2022 | 01/01/2023 | RANJIT GHOSH | 13.69 | 13.55 | 98.95 | 100
10 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Laying distribution system including all types of specials valves street stand post and functional household connection all complete for Augmentation of Chandidas Nanoor Water Supply Scheme in Nanoor Block under Birbhum Division PHE Dte. (Sl.No.4) | AE | JE4 | ORD/000339/2022-2023 | 1070/BHM | 13/05/2022 | 09/11/2022 | G.D. CONSTRUCTION & CO | 484.01 | 299.94 | 61.97 | 88
11 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Supply and delivery of Sluice Valve for Augmentation of Labpur Zone-II W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-5) | AE(HQ) | JE2 | ORD/000344/2023-2024 | 3945/BHM | 03/10/2023 | 02/11/2023 | KALPANA VALVES MFG CO PVT LTD | 8.68 | 8.68 | 100 | 100
12 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Supply and delivery of Sluice Valve for Augmentation of Kirnahar Zone-II W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-3) | AE |  | ORD/000345/2023-2024 | 3952/BHM | 03/10/2023 | 02/11/2023 | RAMESH AND SHANTI ENGINEERING WORKS | 8.19 | 7.94 | 96.97 | 100
13 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Supply and delivery of Sluice Valve for Augmentation of Labpur Zone-I W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-4) | AE |  | ORD/000346/2023-2024 | 3951/BHM | 03/10/2023 | 02/11/2023 | RAMESH AND SHANTI ENGINEERING WORKS | 7.69 | 7.69 | 100 | 100
14 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Supply and delivery of Sluice Valve for Augmentation of Kirnahar Zone-I W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-2) | AE(HQ) | JE2 | ORD/000347/2023-2024 | 3946/BHM | 03/10/2023 | 02/11/2023 | SSPR VALVE MANUFACTURING PVT LTD | 9.43 | 7.82 | 82.85 | 100
15 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Construction of 900cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC pile foundation including pipe connection & allied works for augmentation of Illmbazar W/S Scheme under Birbhum Division, PHE Dte.(As per Departmental Drawing) (Sl. No.2) | AE,Assistant Engineer | JE1 | ORD/000361/2022-2023 | 2770/BHM | 14/12/2022 | 10/09/2023 | APURBA MONDAL | 185.75 | 74.3 | 40 | 30
16 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Laying distribution system for proposed augmentation scheme for Labpur Zone-II Piped Water Supply Scheme, Labpur Block, under Birbhum Division, PHE Dte. | AE | JE3 | ORD/000394/2023-2024 | 4165/BHM | 30/10/2023 | 28/01/2024 | SATYA NARAYAN ENGINEERS CO-OP SOCIETY LTD | 686.13 | 0 | 0 | 20
17 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Continuation work order for Supply and delivery of Sluice Valve for Augmentation of Labpur Zone-II W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte | AE(HQ) | JE2 | ORD/000454/2023-2024 | 21/BHM | 04/01/2024 | 03/02/2024 | KALPANA VALVES MFG CO PVT LTD | 8.68 | 8.68 | 100 | 100
18 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Continuation work order for Supply and delivery of Sluice Valve for Augmentation of Labpur Zone-I W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-4) | AE(HQ) | Estimator | ORD/000466/2023-2024 | 485/BHM | 02/02/2024 | 03/03/2024 | RAMESH AND SHANTI ENGINEERING WORKS | 7.69 | 7.69 | 100 | 100
19 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Continuation Work Order for Supply and delivery of Sluice Valve for Augmentation of Kirnahar Zone-II W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-3) | AE(HQ) | Estimator | ORD/000469/2023-2024 | 503/BHM | 02/02/2024 | 03/03/2024 | RAMESH AND SHANTI ENGINEERING WORKS | 8.19 | 8.19 | 100 | 100
20 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Laying of Distribution system for proposed Augmetation Scheme for Kirnahar ( Zone - II ) and Chandidas Nanoor water Supply scheme on Katowa - Suri Road from Ch. 20.5 to 22.4 km and Naoor - Basapara Road From Node point J34 to J186, J186 to J124, J124 to J33, J33 to J200, J200 to J16, J16 to J9 and J9 to J5 ( by HDD Process with Mechanical Devices and Machinaries required for Treanchless Pipe within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.5) | AE | JE1,JE2,Bolpur Sub-Division,JE3 | ORD/000508/2022-2023 | 92/BHM | 10/01/2023 | 26/03/2023 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 148.83 | 145.55 | 97.79 | 100
21 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Sinking of 02 (Two) no. 250 mm x 200 mm dia. 250 Mtr deep Tube well by Direct Rotary Rig method for Augmentation of Kirnahar Zone - II Water Supply Scheme at Parota Mouja under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Sl. No.5) (2nd Call) | AE | JE2,Bolpur Sub-Division | ORD/000532/2022-2023 | 662/BHM | 28/02/2023 | 30/03/2023 | ANIRUDDHA FARUQUE | 34.05 | 26.64 | 78.26 | 100
22 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Continuation Work Order for Supply and delivery of Sluice Valve for Augmentation of Kirnahar Zone-I W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-2) | AE(HQ) | Estimator,JE2 | ORD/000607/2023-2024 | 907/BHM | 13/03/2024 | 12/04/2024 | SSPR VALVE MANUFACTURING PVT LTD | 9.43 | 0 | 0 | 100
23 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Annual Mtc. of pipeline (Distribution and rising main) for the water supply schemes related to the daily supply of water to the consumers under Birbhum Division, PHE Dte.¿ Chandidas Nanoor Water Supply Scheme (Sl. No.-26) | AE | JE1,JE2,Bolpur Sub-Division,JE3 | ORD/000634/2020-2021 | 1842/BHM | 31/12/2020 | 12/01/2021 | MS KAZIMEHERUDDIN | 2.98 | 0 | 0 | 0
24 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Providing Functional Household Tap Connection (FHTC) for AWC, Health centre, Govt. institution & others from existing distribution system within the command area of Labpur Zone-I & Zone-II Water Supply Scheme within Labpur Block under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 08). | AE | JE3 | ORD/000648/2021-2022 | 71/BSD | 03/03/2022 | 13/03/2022 | ANKITA CHAKRABORTY | 1.09 | 0 | 0 | 50
25 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Laying of Rising main Pipeline for connecting with OHR from tubewell no.-I & II and construction of 2 nos. pump house along with boundary wall and approach road at Headwork site and 2nd tubewell site of Kirnahar Zone-I Piped Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHE Dte. | AE | JE3 | ORD/000669/2023-2024 | 1032/BHM | 15/03/2024 | 11/09/2024 | DIPAK SARKAR | 39.99 | 0 | 0 | 60
26 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Distribution System Relating to Augmentation of Tinor W/S Scheme, Block -Illambazar, District - Birbhum under Birbhum Division, P.H.E. Dte. (Sl. No.-5) | AE | JE1,JE2,Bolpur Sub-Division,JE3 | ORD/000704/2021-2022 | 556/BHM | 08/03/2022 | 04/09/2022 | G.D. CONSTRUCTION & CO | 290.77 | 214.66 | 73.82 | 86
27 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Repairing & Renovation of Pump House No.1, boundary wall, construction of drain, painting of pump house & boundary wall etc. of Labpur(Zone-I)W/S scheme situated at Dwarka under Bolpur Sub-Division, within Birbhum Division,PHE Dte.(Sl.No.03) | AE | JE1,JE2,Bolpur Sub-Division,JE3 | ORD/000720/2021-2022 | 55BH | 17/03/2022 | 15/06/2022 | SYED HASMAT ALI | 4.01 | 0 | 0 | 0
28 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Repairing & Renovation of 2 nos. Pump House with operator room, store room, etc. with coloring of Labpur(Zone-II) W/S Scheme under RWS,Birbhum Sub-Division within Birbhum Division, PHE Dte.(Sl.No.-01) | AE | JE1,JE2,Bolpur Sub-Division,JE3 | ORD/000722/2021-2022 | 53/BH | 17/03/2022 | 15/06/2022 | ARNAB CHANDRA | 4.53 | 0 | 0 | 100
29 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Repairing & Renovation of Pump House, construction of Approach road with culvert,etc. of Labpur (zone-II) W/S Scheme situated at Laghata under RWS Birbhum Sub-Division within Birrbhum Division,PHE Dte.(Sl No. 02) | AE | JE1,JE2,Bolpur Sub-Division,JE3 | ORD/000727/2021-2022 | 54/BH | 17/03/2022 | 15/06/2022 | ANIRUDDHA FARUQUE | 2.31 | 2.23 | 96.68 | 100
30 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Repairing & Renovation of Pump House No.2 & Boundary Wall at Dwarka of Labpur(Zone-I) Water Supply Scheme under RWS Birbhum Sub-Division, PHE Dte. within Birbhum Division, PHE Dte. | AE | JE1,JE2,Bolpur Sub-Division,JE3 | ORD/000776/2021-2022 | 38/BH | 09/03/2022 | 08/04/2022 | ARPAN PANDIT | 2.34 | 0 | 0 | 100
31 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Distribution System Relating to Augmentation of Joydev-Kenduli Water Supply Scheme , Block Illambazar, District, Birbhum, under Birbhum Division, PHE Dte. (Sl. No. - 04) | AE | JE1,JE2,Bolpur Sub-Division,JE3 | ORD/000784/2021-2022 | 1729/BHM | 25/10/2021 | 22/02/2022 | PRANAB KUMAR GHOSH | 84.66 | 22.93 | 27.09 | 45
32 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Allied works for Dismantling of PCC road for Laying of Distribution pipeline and inter-connection to existing pipe line of TINOR Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, Public Health Engineering Department. | AE | JE1 | ORD/000915/2022-2023 | 282/BSD | 25/07/2022 | 14/08/2022 | G.D. CONSTRUCTION & CO | 4.55 | 0 | 0 | 0
33 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Allied works for Dismantling of PCC road for Laying of Distribution pipeline and inter-connection to existing pipeline of Joydev Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, P.H.E. Deptt. | AE | JE1 | ORD/000936/2022-2023 | 238/BSD | 17/06/2022 | 02/07/2022 | PRANAB KUMAR GHOSH | 4.84 | 1.84 | 38.12 | 100
34 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Laying Distribution System for proposed augmentation Scheme for Kirnahar (Zone-II) piped Water Supply Scheme under Nanoor Block, under Birbhum Division, PHE Dte. (Sl. -06) | AE | JE1,JE2,Bolpur Sub-Division,JE3 | ORD/000949/2021-2022 | 648/BHM | 25/03/2022 | 21/09/2022 | M/S ASHA CONSTRUCTION | 325.5 | 208.82 | 64.15 | 34
35 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Distribution System Relating To Augmentation Of Joydev-Kenduli Water Supply Scheme, Block -Illambazar, District - Birbhum, Under Birbhum Division, P.H.E. Dte.. (Sl. No.-4) | AE | JE1,JE2,Bolpur Sub-Division,JE3 | ORD/000964/2021-2022 | 1724/BHM | 25/10/2021 | 22/02/2022 | PRANAB KUMAR GHOSH | 84.66 | 26.12 | 30.85 | 62
36 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 1112/BHM | 10/04/2023 |  | Resource Division | 34.68 | 0 | 0 | 0
37 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2022-2023 | 909/BHM | 26/04/2022 |  | Resource Division | 21.38 | 0 | 0 | 0
38 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000025/2022-2023 | 2206/BHM | 12/10/2022 |  | Resource Division | 82.06 | 0 | 0 | 0
39 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000031/2022-2023 | 2293/BHM | 20/10/2022 |  | Resource Division | 68.75 | 0 | 0 | 0
40 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000068/2021-2022 | 595/BHM | 09/03/2022 |  | Resource Division | 751.34 | 0 | 0 | 0
41 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000177/2023-2024 | 2072/BHM | 14/06/2023 |  | Resource Division | 43.12 | 0 | 0 | 0
42 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000184/2023-2024 | 2279/BHM | 13/07/2023 |  | Resource Division | 142.55 | 0 | 0 | 0
43 | BIRBHUM |  | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Materials Payment |  |  | VCH/001323/2021-2022 | BP-2021-22-355 | 14/03/2022 |  | RESOURCES DIVISION | 602.7 | 0 | 0 | 0
44 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | NEW SERVICE CONNECTION FOR KIRNAHAR WATER SUPPPLY SCHEME Z0NE-I, PH-I. |  |  | BILL/00072/2024-2025 | BP-2024-2025-32 | 20/05/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.08 | 0 | 0 | null
45 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | NEW SERVICE CONNECTION FOR KIRNAHAR WATER SUPPLY SCHEME ZONE-I, PH-II. |  |  | BILL/00229/2024-2025 | BP-24-25-112 | 02/07/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.38 | 0 | 0 | null
46 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Providing Electro-mechanical accessories and others for Augmentation of Lavpur Zone - I Water Supply Scheme under Bolpur Mechanical Division PHE Dte | Assistant Engineer | Junior Engineer | ORD/000242/2023-2024 | 1432/Bol.MD | 11/07/2023 | 25/08/2023 | MITRA ENTERPRISE | 18.87 | 14.78 | 78.36 | 70
47 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Providing Electro-mechanical accessories and others for Augmentation of Lavpur Zone - II Water Supply Scheme under Bolpur Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000246/2023-2024 | 1433/Bol.MD | 11/07/2023 | 25/08/2023 | M/S SWAPAN BANERJEE | 28.36 | 22.22 | 78.35 | 70
48 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Providing Electro-mechanical accessories and others for Augmentation of Kirnahar Zone - I Water Supply Scheme under Bolpur Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000249/2023-2024 | 1434/Bol.MD | 11/07/2023 | 25/08/2023 | SINHA ELECTRICALS | 19.43 | 12.06 | 62.1 | 30
49 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Providing Electro-mechanical accessories and others for Augmentation of Kirnahar Zone - II Water Supply Scheme under Bolpur Mechanical Division PHE Dte.. | Assistant Engineer | Junior Engineer | ORD/000250/2023-2024 | 1435/Bol.MD | 11/07/2023 | 25/08/2023 | EASTERN INDIA SALES & SERVICE | 18.86 | 9.54 | 50.57 | 30
50 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (250 mm x 150 mm x 300 Mtrs. Depth ) by utilising Hired Rig Machine at Bipratikuri PWSS (at defunct 2nd tube well site) , Block - Labhpur, (under Retrofitting of Lavpur Block) under Bolpur Mechanical Division, P.H.E. Dte | Driller in Charge | Junior Engineer | ORD/000337/2023-2024 | 1645/Bol.MD | 25/07/2023 | 23/09/2023 | SATYAJIT GHOSH | 21.43 | 20.95 | 97.78 | 100
51 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (250 mm x 150 mm x 300 Mtrs. Depth ) by utilising Hired Rig Machine at Kirnahar Zone - I PWSS (at Debogram) , Block - Nanoor, (under Augmentation of 6 nos. schemes of Lavpur PWSS, Illambazar PWSS, Joydev Kenduli PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS) under Bolpur Mechanical Division, P.H.E. Dte | Driller in Charge | Junior Engineer | ORD/000338/2023-2024 | 1646/Bol.MD | 25/07/2023 | 23/09/2023 | SATYAJIT GHOSH | 42.86 | 41.46 | 96.75 | 100
52 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (250 mm x 150 mm x 300 Mtrs. Depth ) by utilising Hired Rig Machine at Lavpur Zone - I & Zone - II PWSS (at Dwarka & Zone - II at Head Works site) , Block - Lavpur, (under Augmentation of 6 nos. schemes of Lavpur PWSS, Illambazar PWSS, Joydev Kenduli PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS) under Bolpur Mechanical Division, P.H.E. Dte | Driller in Charge | Junior Engineer | ORD/000339/2023-2024 | 1647/Bol.MD | 25/07/2023 | 23/09/2023 | SATYAJIT GHOSH | 42.86 | 26 | 60.67 | 100
53 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (250 mm x 150 mm x 300 Mtrs. Depth ) by utilising Hired Rig Machine at Illambazar and Tinoor PWSS (at Head Works site) , Block - Illambazar (under Augmentation of 6 nos. schemes of Lavpur PWSS, Illambazar PWSS, Joydev Kenduli PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS) under Bolpur Mechanical Division, P.H.E. Dte. | Driller in Charge | Junior Engineer | ORD/000340/2023-2024 | 1648/Bol.MD | 25/07/2023 | 23/09/2023 | SATYAJIT GHOSH | 42.86 | 37.75 | 88.09 | 100
54 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Providing Electro-mechanical accessories including other allied works for Augmentation of ILLAMBAZAR PWSS under Bolpur Mechanical Division PHE Dte. Block : Illambazar, Dist : Birbhum. | Assistant Engineer-III | Junior Engineer | ORD/000493/2023-2024 | 2248/Bol.MD | 13/09/2023 | 12/11/2023 | EASTERN INDIA SALES & SERVICE | 30.28 | 10.32 | 34.07 | 60
55 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Providing Electro-mechanical accessories including other allied works for Augmentation of TINOOR Piped Water Supply Scheme under Bolpur Mechanical Division PHE Dte. Block : Illambazar, Dist : Birbhum. | Assistant Engineer-III | Junior Engineer | ORD/000494/2023-2024 | 2249/Bol.MD | 13/09/2023 | 12/11/2023 | DEY ENTERPRISE | 21.4 | 0 | 0 | 0
56 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Supply and installation of Pumps and other electro-mechanical accessories for Augmentation of Nanoor water supply scheme T.W. No.- 1 under Bolpur Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000495/2023-2024 | 2250/Bol.MD | 13/09/2023 | 12/11/2023 | STANDARD ELECTRICALS | 5.78 | 0 | 0 | 0
57 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Providing Electro-mechanical accessories including other allied works for Augmentation of JOYDEV-KENDULI Piped Water Supply Scheme under Bolpur Mechanical Division PHE Dte. Block : Illambazar, Dist : Birbhum. | Assistant Engineer | Junior Engineer | ORD/000984/2023-2024 | 3600/BOL.MD | 12/12/2023 | 11/03/2024 | RSA ENTERPRISE | 21.19 | 0 | 0 | 0
58 | BIRBHUM |  | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division | SM/10320 | Augmentation | Supply & Installation of Motor control Panels at the Kirnahar Water Supply Scheme under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer (HQ) | Junior Engineer | ORD/001260/2023-2024 | 559/BOL.MD | 15/03/2024 | 14/04/2024 | SINHA ELECTRICALS | 2.92 | 1.46 | 50 | 100
Total | [13 empty] | 6697.4 | 2088.17 | 31.18