## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Birbhum Division | Paschim Naopara and Adjoining Mouzas PWSS | SM/12458 | New | Different works related to water supply scheme at PASCHIM NAOPARA, PHULUR & PURBA SIUR its adjoining mouzas water supply scheme within SAINTHIA Block under Birbhum Division, PHE Dte. | AE | JE | ORD/000189/2023-2024 | 2262/BHM | 12/07/2023 | 07/04/2024 | B RAI CONSTRUCTION COMPANY | 1402.44 | 140.55 | 10.02 | 25
2 | BIRBHUM | Sainthia | Birbhum Division | Paschim Naopara and Adjoining Mouzas PWSS | SM/12458 | New | Material Requisition To Resource Division |  |  | RTOR000068/2022-2023 | 1422/BHM | 24/04/2023 |  | Resource Division | 40.92 | 0 | 0 | 0
3 | BIRBHUM | Sainthia | Bolpur Mechanical | Paschim Naopara and Adjoining Mouzas PWSS | SM/12458 | New | New service connection at Paschim Nowapara PH-II W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/02182/2023-2024 | BP-2023-24-319 | 18/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.69 | 0 | 0 | null
4 | BIRBHUM | Sainthia | Bolpur Mechanical | Paschim Naopara and Adjoining Mouzas PWSS | SM/12458 | New | WBSEDCL QUOTATION FOR PASCHIM NOWAPARA PH NO-I |  |  | BILL/02236/2023-2024 | null | 14/03/2024 |  | WBSEDCL | 5.62 | 0 | 0 | 0
5 | BIRBHUM | Sainthia | Bolpur Mechanical | Paschim Naopara and Adjoining Mouzas PWSS | SM/12458 | New | New service connection at Paschim Nowapara PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/02240/2023-2024 | BP-2023-24-320 | 19/03/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.62 | 0 | 0 | null
6 | BIRBHUM | Sainthia | Bolpur Mechanical | Paschim Naopara and Adjoining Mouzas PWSS | SM/12458 | New | Providing Electro-mechanical accessories and others for Paschim Naopara & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000433/2023-2024 | 2095/Bol.MD | 22/08/2023 | 21/10/2023 | BIRBHUM ELECTRIC WORKS | 27.94 | 18.69 | 66.89 | 50
Total | [13 empty] | 1487.23 | 159.23 | 10.71