## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai - II | Birbhum Division | BONHA PIPED WATER SUPPLY SCHEME at Murarai-II Block,District Birbhum Division. | SM/12591 | New | Different Works related to water supply scheme at Bonha & its adjoining mouzas water supply scheme within Murarai-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE | JE | ORD/000028/2023-2024 | 1216/BHM | 12/04/2023 | 07/01/2024 | TAPAN KUMAR DATTA | 293.99 | 38.02 | 12.93 | 20
2 | BIRBHUM | Murarai - II | Birbhum Division | BONHA PIPED WATER SUPPLY SCHEME at Murarai-II Block,District Birbhum Division. | SM/12591 | New | Material Requisition To Resource Division |  |  | RTOR000039/2023-2024 | 1472/BHM | 25/04/2023 |  | Resource Division | 53.39 | 0 | 0 | 0
3 | BIRBHUM | Murarai - II | Bolpur Mechanical | BONHA PIPED WATER SUPPLY SCHEME at Murarai-II Block,District Birbhum Division. | SM/12591 | New | WBSEDCL QUOTATION FOR BONHA P H NO.I WS SCHEME |  |  | BILL/01594/2023-2024 | BP-23-24-228 | 15/01/2024 |  | WBSEDCL | 3.6 | 0 | 0 | 0
4 | BIRBHUM | Murarai - II | Bolpur Mechanical | BONHA PIPED WATER SUPPLY SCHEME at Murarai-II Block,District Birbhum Division. | SM/12591 | New | Providing Electro-mechanical accessories and others for Bonha PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000940/2023-2024 | 3301/BOL.MD | 29/09/2023 | 28/11/2023 | QUAZI NOZRUL ISLAM | 28.83 | 11.39 | 39.51 | 60
Total | [13 empty] | 379.81 | 49.41 | 13.01