## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai - II | Birbhum Division | JOGAI PIPED WATER SUPPLY SCHEME. | SM/12593 | New | Different works related to water supply scheme at JOGAI & its adjoining mouzas water supply scheme within Murarai-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte.(2nd Call) | AE | JE2 | ORD/000064/2023-2024 | 1308/BHM | 19/04/2023 | 14/01/2024 | QUAZI SIRAJUL ISLAM. | 257.76 | 48.39 | 18.77 | 12
2 | BIRBHUM | Murarai - II | Birbhum Division | JOGAI PIPED WATER SUPPLY SCHEME. | SM/12593 | New | Material Requisition To Resource Division |  |  | RTOR000048/2023-2024 | 1458/BHM | 25/04/2023 |  | Resource Division | 10.24 | 0 | 0 | 0
3 | BIRBHUM | Murarai - II | Bolpur Mechanical | JOGAI PIPED WATER SUPPLY SCHEME. | SM/12593 | New | WBSEDCL QUOTATION FOR JOGAI P H NO. I WS SCHEME |  |  | BILL/01598/2023-2024 | BP-23-24-229 | 15/01/2024 |  | WBSEDCL | 3.25 | 0 | 0 | 0
4 | BIRBHUM | Murarai - II | Bolpur Mechanical | JOGAI PIPED WATER SUPPLY SCHEME. | SM/12593 | New | WBSEDCL QUOTATION FOR JOGAI P H NO .II WS SCHEME |  |  | BILL/01599/2023-2024 | BP-23-24-230 | 15/01/2024 |  | WBSEDCL | 3.16 | 0 | 0 | 0
5 | BIRBHUM | Murarai - II | Bolpur Mechanical | JOGAI PIPED WATER SUPPLY SCHEME. | SM/12593 | New | Providing Electro-mechanical accessories and others for Jagoi PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000942/2023-2024 | 3303/BOL.MD | 29/09/2023 | 28/11/2023 | SUNRISE ENGINEERING CORPORATION | 28.91 | 0 | 0 | 0
Total | [13 empty] | 303.32 | 48.39 | 15.95