## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai - I,Murarai - II | Birbhum Division | Chanchali piped water supply scheme. | SM/12683 | New | Different works related to water supply scheme at Chanchali, Dakshin Kashila & Mahurapur and its adjoining mouzas water supply scheme within Murarai-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE1 | ORD/000081/2023-2024 | 1424/BHM | 25/04/2023 | 20/01/2024 | SUPRITI ENTERPRISE | 1680 | 122.77 | 7.31 | 30
2 | BIRBHUM | Murarai - I,Murarai - II | Birbhum Division | Chanchali piped water supply scheme. | SM/12683 | New | Material Requisition To Resource Division |  |  | RTOR000085/2023-2024 | 1487/BHM | 25/04/2023 |  | Resource Division | 157.22 | 0 | 0 | 0
3 | BIRBHUM | Murarai - I,Murarai - II | Bolpur Mechanical | Chanchali piped water supply scheme. | SM/12683 | New | Quotation deposit for empowering Chanchali P/H-I Water Supply Scheme, Nandigram Kalitala in Paikar CCC under Bolpur Mechanical Division, PHE Dte |  |  | BILL/00152/2024-2025 | BP-2024-2025-79 | 13/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.5 | 0 | 0 | null
4 | BIRBHUM | Murarai - I,Murarai - II | Bolpur Mechanical | Chanchali piped water supply scheme. | SM/12683 | New | Providing Electro-mechanical accessories and others for CHANCHALI piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000532/2023-2024 | 2173/Bol.MD | 01/09/2023 | 31/10/2023 | M/S. SREEJIT ENTERPRISE | 30.68 | 9.76 | 31.82 | 40
Total | [13 empty] | 1871.4 | 132.53 | 7.08