## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai - II | Birbhum Division | Kulara Piped Water Supply Scheme. | SM/12695 | New | Different works related to water supply scheme at KULARA & its adjoining mouzas water supply scheme within Murarai-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte.(2nd Call) | AE | JE1 | ORD/000034/2023-2024 | 1098/BHM | 06/04/2023 | 01/01/2024 | M/S H. R. CONSTRUCTION | 263.91 | 24.4 | 9.24 | 45
2 | BIRBHUM | Murarai - II | Birbhum Division | Kulara Piped Water Supply Scheme. | SM/12695 | New | Material Requisition To Resource Division |  |  | RTOR000102/2023-2024 | 1504/BHM | 25/04/2023 |  | Resource Division | 8.75 | 0 | 0 | 0
3 | BIRBHUM | Murarai - II | Bolpur Mechanical | Kulara Piped Water Supply Scheme. | SM/12695 | New | Quotation deposit for empowering Kulora Water Supply Scheme P/H -II in Paikar CCC under Bolpur Mechanical Division, PHE Dte |  |  | BILL/00090/2024-2025 | BP-2024-2025-43 | 28/05/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.48 | 0 | 0 | null
4 | BIRBHUM | Murarai - II | Bolpur Mechanical | Kulara Piped Water Supply Scheme. | SM/12695 | New | WBSEDCL QUOTATION FOR KULARA P H NO.I WS SCHEME |  |  | BILL/01595/2023-2024 | BP-23-24-227 | 15/01/2024 |  | WBSEDCL | 2.99 | 0 | 0 | 0
5 | BIRBHUM | Murarai - II | Bolpur Mechanical | Kulara Piped Water Supply Scheme. | SM/12695 | New | Providing Electro-mechanical accessories and others for KULARA piped water supply scheme, Murarai-II block, under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000546/2023-2024 | 2142/Bol.MD | 25/08/2023 | 24/10/2023 | KAMAKHYA ENTERPRISE | 27.21 | 10.78 | 39.63 | 70
6 | BIRBHUM | Murarai - II | Bolpur Mechanical | Kulara Piped Water Supply Scheme. | SM/12695 | New | Supply and installation of manual operated Motor control panel for Kulara water supply scheme (Amdol Pump House-III) of Murarai-II Block under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001281/2023-2024 | 178/BMSD(D) | 18/03/2024 | 17/04/2024 | M/S M3 SOLUTION | 2.6 | 0.9 | 34.65 | 100
7 | BIRBHUM | Murarai - II | Bolpur Mechanical | Kulara Piped Water Supply Scheme. | SM/12695 | New | Supply, delivery and installation of servo motor operated copper wound line voltage corrector for Kulara water supply scheme (Amdol Pump House-III) of Murarai-II Block under Bolpur Mechanical Division, PHE Dte. |  |  | ORD/001282/2023-2024 | 179/BMSD(D) | 18/03/2024 | 17/04/2024 | SUNIL RABIDAS | 3.18 | 0 | 0 | 0
Total | [13 empty] | 313.13 | 36.08 | 11.52