## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai - I | Birbhum Division | Mahurapur and Adjoining Mouzas PWSS | SM/12697 | New | Estimate for restoration charges for laying PHE pipeline from 3.5 KM to 6.5 KM of rajgram Maharapur road under rampurhat highway sub division of Birbhum highway Division-Iin the dist of Birbhum during the year 2023-24 |  |  | BILL/00735/2024-2025 | null | 10/09/2024 |  | EXECUTIVE ENGINEER BIRBHUM HIGHWAY DIVISION-I P.W (ROADS) DIRECTORATE | 22 | 0 | 0 | 0
2 | BIRBHUM | Murarai - I | Birbhum Division | Mahurapur and Adjoining Mouzas PWSS | SM/12697 | New | Different works related to water supply scheme at Chanchali, Dakshin Kashila & Mahurapur and its adjoining mouzas water supply scheme within Murarai-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE1 | ORD/000081/2023-2024 | 1424/BHM | 25/04/2023 | 20/01/2024 | SUPRITI ENTERPRISE | 1680 | 0 | 0 | 30
3 | BIRBHUM | Murarai - I | Birbhum Division | Mahurapur and Adjoining Mouzas PWSS | SM/12697 | New | Acceptance Cum Work Order for Supply and delivery of Sluice Valve for Mahurapur and Adjoining Mouzas PWSS under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte | AE(HQ) | JE1 | ORD/000635/2023-2024 | 948/BHM | 14/03/2024 | 13/04/2024 | MAKALI ENGINEERING CORPORATION | 9.71 | 0 | 0 | 0
4 | BIRBHUM | Murarai - I | Birbhum Division | Mahurapur and Adjoining Mouzas PWSS | SM/12697 | New | Material Requisition To Resource Division |  |  | RTOR000018/2023-2024 | 1435/BHM | 25/04/2023 |  | Resource Division | 48.04 | 0 | 0 | 0
5 | BIRBHUM | Murarai - I | Bolpur Mechanical | Mahurapur and Adjoining Mouzas PWSS | SM/12697 | New | Providing Electro-mechanical accessories and others for MAHURAPUR piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000902/2023-2024 | 3297/Bol.MD | 29/09/2023 | 28/11/2023 | MITRA ENTERPRISE | 30.63 | 0 | 0 | 0
Total | [13 empty] | 1790.37 | 0 | 0