## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nalhati - I | Birbhum Division | KANIOR PIPED WATER SUPPLY SCHEME. | SM/12831 | New | Different works related to water supply scheme at KANIOR, KOGRAM & KUSHIPUR PWSS & its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE2 | ORD/000596/2022-2023 | 1059/BHM | 31/03/2023 | 26/12/2023 | SK ALIM | 1229.19 | 0 | 0 | 25
2 | BIRBHUM | Nalhati - I | Birbhum Division | KANIOR PIPED WATER SUPPLY SCHEME. | SM/12831 | New | Material Requisition To Resource Division |  |  | RTOR000014/2023-2024 | 1430/BHM | 25/04/2023 |  | Resource Division | 14.24 | 0 | 0 | 0
3 | BIRBHUM | Nalhati - I | Bolpur Mechanical | KANIOR PIPED WATER SUPPLY SCHEME. | SM/12831 | New | WBSEDCL QUOTATION FOR KANIOR |  |  | BILL/01574/2023-2024 | BP-23-24-209 | 04/01/2024 |  | WBSEDCL | 3.26 | 0 | 0 | 0
4 | BIRBHUM | Nalhati - I | Bolpur Mechanical | KANIOR PIPED WATER SUPPLY SCHEME. | SM/12831 | New | WBSEDCL QUOTATION FOR KANIOR |  |  | BILL/01575/2023-2024 | BP-23-24-208 | 04/01/2024 |  | WBSEDCL | 0.44 | 0 | 0 | 0
5 | BIRBHUM | Nalhati - I | Bolpur Mechanical | KANIOR PIPED WATER SUPPLY SCHEME. | SM/12831 | New | Supply and Delivery of Sub-Mersible Pumping Machineries inconection with Providing Electro-mechanical accessories and others for Kanior PWSS at Nalhati - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000002/2024-2025 | 685./AE-III | 08/04/2024 | 22/04/2024 | GOENKA ENTERPRISE | 1.58 | 1.01 | 64 | 100
6 | BIRBHUM | Nalhati - I | Bolpur Mechanical | KANIOR PIPED WATER SUPPLY SCHEME. | SM/12831 | New | Providing Electro-mechanical accessories and others for Kanior PWSS at Nalhati - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000915/2023-2024 | 3542/BOL.MD | 30/11/2023 | 29/01/2024 | GOENKA ENTERPRISE | 30.69 | 12.21 | 39.79 | 60
Total | [13 empty] | 1279.39 | 13.22 | 1.03