## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai - II | Birbhum Division | JIJIGRAM PIPED WATER SUPPLY SCHEME. | SM/12837 | New | Different works related to water supply scheme at Jijigram, Math Basori & Bilaspur and its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE3 | ORD/000191/2023-2024 | 3019/BHM | 14/07/2023 | 09/04/2024 | SUNIL RABI DAS | 1250.5 | 129.23 | 10.33 | 25
2 | BIRBHUM | Murarai - II | Birbhum Division | JIJIGRAM PIPED WATER SUPPLY SCHEME. | SM/12837 | New | Material Requisition To Resource Division |  |  | RTOR000083/2023-2024 | 1491/BHM | 25/04/2023 |  | Resource Division | 53.18 | 0 | 0 | 0
3 | BIRBHUM | Murarai - II | Bolpur Mechanical | JIJIGRAM PIPED WATER SUPPLY SCHEME. | SM/12837 | New | WBSEDCL QUOTATION FOR UTTAR JIJIGRAM P H NO.II WS SCHEME |  |  | BILL/01470/2023-2024 | BP-23-24-194 | 14/12/2023 |  | WBSEDCL | 3.14 | 0 | 0 | 0
4 | BIRBHUM | Murarai - II | Bolpur Mechanical | JIJIGRAM PIPED WATER SUPPLY SCHEME. | SM/12837 | New | WBSEDCL QUOTATION FOR UTTAR JIJIGRAM P H NO.I WS SCHEME |  |  | BILL/01471/2023-2024 | BP-23-24-193 | 14/12/2023 |  | WBSEDCL | 3.58 | 0 | 0 | 0
5 | BIRBHUM | Murarai - II | Bolpur Mechanical | JIJIGRAM PIPED WATER SUPPLY SCHEME. | SM/12837 | New | Providing Electro-mechanical accessories and others for Jijigram PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000389/2023-2024 | 1928/Bol.MD | 11/08/2023 | 10/10/2023 | SUNIL RABIDAS | 27.41 | 18.82 | 68.68 | 70
6 | BIRBHUM | Murarai - II | Bolpur Mechanical | JIJIGRAM PIPED WATER SUPPLY SCHEME. | SM/12837 | New | Hiring and Running of Diesel Generator set at P. H. No- II, of Jajigram water supply scheme under Bolpur Mechanical Division, PHE. Dte | Assistant Engineer | Junior Engineer | ORD/001362/2023-2024 | 48/BMSD(D) | 05/02/2024 | 15/02/2024 | SUNIL RABIDAS | 0.98 | 0 | 0 | 100
7 | BIRBHUM | Murarai - II | Bolpur Mechanical | JIJIGRAM PIPED WATER SUPPLY SCHEME. | SM/12837 | New | Hiring and Running of Diesel Generator set at P.H. No. II, of Jajigram water supply scheme under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001363/2023-2024 | 59/BMSD(D) | 15/02/2024 | 25/02/2024 | SUNIL RABIDAS | 0.98 | 0 | 0 | 100
8 | BIRBHUM | Murarai - II | Bolpur Mechanical | JIJIGRAM PIPED WATER SUPPLY SCHEME. | SM/12837 | New | Hiring and Running of Diesel Generator set at P.H. No. I, of Jajigram water supply scheme under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001364/2023-2024 | 62/BMSD(D) | 15/02/2024 | 25/02/2024 | SUNIL RABIDAS | 0.98 | 0 | 0 | 100
9 | BIRBHUM | Murarai - II | Bolpur Mechanical | JIJIGRAM PIPED WATER SUPPLY SCHEME. | SM/12837 | New | Hiring and Running of Diesel Generator set at P.H. No.II, of Jajigram water supply scheme under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001366/2023-2024 | 84/BMSD(D) | 23/02/2024 | 04/03/2024 | SUNIL RABIDAS | 0.98 | 0 | 0 | 100
10 | BIRBHUM | Murarai - II | Bolpur Mechanical | JIJIGRAM PIPED WATER SUPPLY SCHEME. | SM/12837 | New | Hiring and Running of Diesel Generator set at P.H. No. I, of Jajigram water supply scheme under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001367/2023-2024 | 90/BMSD(D) | 28/02/2024 | 06/03/2024 | SUNIL RABIDAS | 0.68 | 0 | 0 | 100
11 | BIRBHUM | Murarai - II | Bolpur Mechanical | JIJIGRAM PIPED WATER SUPPLY SCHEME. | SM/12837 | New | Hiring and Running of Diesel Generator set at P.H. No. II, of Jajigram water supply scheme under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001369/2023-2024 | 101/BMSD(D) | 01/03/2024 | 03/03/2024 | SUNIL RABIDAS | 0.2 | 0 | 0 | 100
12 | BIRBHUM | Murarai - II | Central Drilling | JIJIGRAM PIPED WATER SUPPLY SCHEME. | SM/12837 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm x 200mm x 150mtrs depth) by utilising Departmental Machineries for Jijigram PWSS,TW-II , Murarai-II Block under Birbhum District ,CDD,P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000448/2022-2023 | 1380/CDD | 24/11/2022 | 24/12/2022 | OSMAN SEKH | 10.67 | 8.27 | 77.51 | 100
13 | BIRBHUM | Murarai - II | Central Drilling | JIJIGRAM PIPED WATER SUPPLY SCHEME. | SM/12837 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm x 200mm x 150mtrs depth) by utilising Departmental Machineries for Jijigram PWSS,TW-I , Murarai-II Block under Birbhum District ,CDD,P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000449/2022-2023 | 1379/CDD | 24/11/2022 | 24/12/2022 | OSMAN SEKH | 10.67 | 8.27 | 77.51 | 100
Total | [13 empty] | 1363.94 | 164.6 | 12.07