## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Murarai - II | Birbhum Division | MITRAPUR WATER SUPPLY SCHEME. | SM/12892 | New | Restoration charges for laying of PHE pipeline from Chainage 9.50 KM (Barsliapukur) to 12.24 KM (end point) of Murarai Mitrapur Road under Rampurhat Highrway Sub-Division of Birbhunr Highrvay Division-1. in the District of Bir.bhurn during the year 2024-25 |  |  | BILL/00737/2024-2025 | null | 10/09/2024 |  | EXECUTIVE ENGINEER BIRBHUM HIGHWAY DIVISION-I P.W (ROADS) DIRECTORATE | 9.82 | 0 | 0 | 0
2 | BIRBHUM | Murarai - II | Birbhum Division | MITRAPUR WATER SUPPLY SCHEME. | SM/12892 | New | Different works related to water supply scheme at MITRAPUR & its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE | JE1 | ORD/000277/2023-2024 | 3597/BHM | 21/08/2023 | 17/05/2024 | SUNIL RABI DAS | 635.29 | 0 | 0 | 0
3 | BIRBHUM | Murarai - II | Birbhum Division | MITRAPUR WATER SUPPLY SCHEME. | SM/12892 | New | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 1432/BHM | 25/04/2023 |  | Resource Division | 40.94 | 0 | 0 | 0
4 | BIRBHUM | Murarai - II | Birbhum Division | MITRAPUR WATER SUPPLY SCHEME. | SM/12892 | New | Material Requisition To Resource Division |  |  | RTOR000045/2023-2024 | 1496/BHM | 25/04/2023 |  | Resource Division | 40.94 | 0 | 0 | 0
5 | BIRBHUM | Murarai - II | Bolpur Mechanical | MITRAPUR WATER SUPPLY SCHEME. | SM/12892 | New | Quotation deposit for empowering Mitrapur P/H-I Water Supply Scheme in Paikar CCC under Bolpur Mechanical Division, PHE Dte. |  |  | BILL/00150/2024-2025 | BP-2024-2025-77 | 13/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.64 | 0 | 0 | null
6 | BIRBHUM | Murarai - II | Bolpur Mechanical | MITRAPUR WATER SUPPLY SCHEME. | SM/12892 | New | Providing Electro-mechanical accessories and others for Mitrapur PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000945/2023-2024 | 3306/BOL.MD | 29/09/2023 | 28/11/2023 | MITRA ENTERPRISE | 30.25 | 0 | 0 | 0
Total | [13 empty] | 760.9 | 0 | 0