## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nalhati - I | Birbhum Division | KOGRAM PIPED WATER SUPPLY SCHEME. | SM/12894 | New | Different works related to water supply scheme at KANIOR, KOGRAM & KUSHIPUR PWSS & its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE2 | ORD/000596/2022-2023 | 1059/BHM | 31/03/2023 | 26/12/2023 | SK ALIM | 1229.19 | 43.8 | 3.56 | 25
2 | BIRBHUM | Nalhati - I | Birbhum Division | KOGRAM PIPED WATER SUPPLY SCHEME. | SM/12894 | New | Material Requisition To Resource Division |  |  | RTOR000054/2023-2024 | 1572/BHM | 26/04/2023 |  | Resource Division | 16.61 | 0 | 0 | 0
3 | BIRBHUM | Nalhati - I | Bolpur Mechanical | KOGRAM PIPED WATER SUPPLY SCHEME. | SM/12894 | New | WBSEDCL QUOTATION FOR SKOGRAM WS SCHEME |  |  | BILL/01606/2023-2024 | BP-23-24-236 | 29/01/2024 |  | WBSEDCL | 2.85 | 0 | 0 | 0
4 | BIRBHUM | Nalhati - I | Bolpur Mechanical | KOGRAM PIPED WATER SUPPLY SCHEME. | SM/12894 | New | Providing Electro-mechanical accessories and others for Kogram PWSS at Nalhati - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000913/2023-2024 | 3541/BOL.MD | 30/11/2023 | 29/01/2024 | A.S.ENTERPRISE | 27.56 | 10.92 | 39.64 | 50
Total | [13 empty] | 1276.2 | 54.73 | 4.29