## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nalhati - I | Birbhum Division | SARIHA PIPED WATER SUPPLY SCHEME | SM/12900 | New | Different works related to water supply scheme at Majhkaltia, Sahira & KANAPIUR PWSS & its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE | JE2 | ORD/000075/2023-2024 | 1348/BHM | 20/04/2023 | 15/01/2024 | M/S GOUTAM DAS | 1594.34 | 0 | 0 | 28
2 | BIRBHUM | Nalhati - I | Birbhum Division | SARIHA PIPED WATER SUPPLY SCHEME | SM/12900 | New | Material Requisition To Resource Division |  |  | RTOR000170/2023-2024 | 2177/BHM | 23/06/2023 |  | Resource Division | 14.08 | 0 | 0 | 0
3 | BIRBHUM | Nalhati - I | Bolpur Mechanical | SARIHA PIPED WATER SUPPLY SCHEME | SM/12900 | New | Providing Electro-mechanical accessories and others for Sariha PWSS at Nalhati - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000881/2023-2024 | 3366/BOL.MD | 11/10/2023 | 10/12/2023 | T.D.K. ENTERPRISE | 27.35 | 0 | 0 | 0
Total | [13 empty] | 1635.77 | 0 | 0