## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Suri - II | Birbhum Division | KASHERHAT PIPED WATER SUPPLY SCHEME. | SM/12903 | New | Different works for KASHERHAT & Sehana and its adjoining mouzas water supply scheme within SURI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE | ORD/000383/2023-2024 | 4138/BHM | 18/10/2023 | 14/07/2024 | PASCON | 975.41 | 0 | 0 | 0
2 | BIRBHUM | Suri - II | Birbhum Division | KASHERHAT PIPED WATER SUPPLY SCHEME. | SM/12903 | New | Material Requisition To Resource Division |  |  | RTOR000040/2022-2023 | 1387/BHM | 24/04/2023 |  | Resource Division | 20.85 | 0 | 0 | 0
3 | BIRBHUM | Suri - II | Bolpur Mechanical | KASHERHAT PIPED WATER SUPPLY SCHEME. | SM/12903 | New | New service connection at Kasherhat PH-I W/S scheme Block-Suri II under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/00130/2024-2025 | BP-2024-2025-63 | 05/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.72 | 0 | 0 | null
4 | BIRBHUM | Suri - II | Bolpur Mechanical | KASHERHAT PIPED WATER SUPPLY SCHEME. | SM/12903 | New | New service connection at Kasherhat PH-II W/S scheme Block-Suri II under Bolpur Mechanical Division,PHE Dte. |  |  | BILL/00132/2024-2025 | BP-2024-2025-64 | 05/06/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.21 | 0 | 0 | null
5 | BIRBHUM | Suri - II | Bolpur Mechanical | KASHERHAT PIPED WATER SUPPLY SCHEME. | SM/12903 | New | Providing Electro-mechanical accessories and others for Kasherhat PWSS at Suri - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000398/2023-2024 | 2076/BOL.MD. | 21/08/2023 | 20/10/2023 | MITRA ENTERPRISE | 28.66 | 9.98 | 34.82 | 80
Total | [13 empty] | 1038.84 | 9.98 | 0.96