## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nalhati - II | Birbhum Division | Prasadpur Piped Water Supply Scheme | SM/13478 | New | Different works related to water supply scheme at NAWAPARA & PRASADPUR and its adjoining mouzas water supply scheme within NALHATI-II Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE2 | ORD/000207/2023-2024 | 3257/BHM | 26/07/2023 | 21/04/2024 | MANASH GHOSH | 866.09 | 91.84 | 10.6 | 5
2 | BIRBHUM | Nalhati - II | Birbhum Division | Prasadpur Piped Water Supply Scheme | SM/13478 | New | Preparation and submission of DPR for (Prasadpur) Water Supply Scheme under Nalhati-II Development Block. | AE | JE2 | ORD/000759/2022-2023 | 232/AE/NSD | 21/04/2022 | 05/06/2022 | MS SOBHA AND CO | 4.81 | 2.41 | 50 | 100
3 | BIRBHUM | Nalhati - II | Birbhum Division | Prasadpur Piped Water Supply Scheme | SM/13478 | New | Material Requisition To Resource Division |  |  | RTOR000110/2023-2024 | 1509/BHM | 26/04/2023 |  | Resource Division | 9.92 | 0 | 0 | 0
4 | BIRBHUM | Nalhati - II | Bolpur Mechanical | Prasadpur Piped Water Supply Scheme | SM/13478 | New | Providing Electro-mechanical accessories and others for Prasadpur PWSS at Nalhati - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000464/2023-2024 | 2138/Bol.MD | 25/08/2023 | 24/10/2023 | QUAZI NOZRUL ISLAM | 44.39 | 9.65 | 21.75 | 40
5 | BIRBHUM | Nalhati - II | Bolpur Mechanical | Prasadpur Piped Water Supply Scheme | SM/13478 | New | Supply and Delivery of Open well Submersible Pumping Machineries and allied accessories for Prasadpur PWSS, (Block- Nalhati - II) under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000524/2024-2025 | 3783/BOL.MD | 12/09/2024 | 12/10/2024 | M/S. UTTAM KUMAR CHATTERJEE | 28.98 | 0 | 0 | 0
Total | [13 empty] | 954.2 | 103.9 | 10.89