## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nalhati - II | Birbhum Division | Nawapara Piped Water Supply Scheme | SM/13479 | New | Different works related to water supply scheme at NAWAPARA & PRASADPUR and its adjoining mouzas water supply scheme within NALHATI-II Block including supply of all labour & materials under Birbhum Division, PHE Dte. | AE | JE2 | ORD/000207/2023-2024 | 3257/BHM | 26/07/2023 | 21/04/2024 | MANASH GHOSH | 866.09 | 0 | 0 | 5
2 | BIRBHUM | Nalhati - II | Birbhum Division | Nawapara Piped Water Supply Scheme | SM/13479 | New | Preparation and submission of DPR for (Nawapara) Water Supply Scheme under Nalhati-II Development Block. | AE | JE2 | ORD/000758/2022-2023 | 231/AE/NSD | 21/04/2022 | 05/06/2022 | MS SOBHA AND CO | 4.6 | 2.3 | 50 | 100
3 | BIRBHUM | Nalhati - II | Birbhum Division | Nawapara Piped Water Supply Scheme | SM/13479 | New | Material Requisition To Resource Division |  |  | RTOR000111/2023-2024 | 1502/BHM | 25/04/2023 |  | Resource Division | 65.11 | 0 | 0 | 0
4 | BIRBHUM | Nalhati - II | Bolpur Mechanical | Nawapara Piped Water Supply Scheme | SM/13479 | New | WBSEDCL QUOTATION FOR NOAPARA P H .II WS SCHEME |  |  | BILL/01600/2023-2024 | BP-23-24-234 | 29/01/2024 |  | WBSEDCL | 3.42 | 0 | 0 | 0
5 | BIRBHUM | Nalhati - II | Bolpur Mechanical | Nawapara Piped Water Supply Scheme | SM/13479 | New | WBSEDCL QUOTATION FOR NOAPARA WS SCHEME |  |  | BILL/01601/2023-2024 | BP-23-24-233 | 15/01/2024 |  | WBSEDCL | 4.14 | 0 | 0 | 0
6 | BIRBHUM | Nalhati - II | Bolpur Mechanical | Nawapara Piped Water Supply Scheme | SM/13479 | New | Providing Electro-mechanical accessories and others for Nawpara PWSS at Nalhati - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000463/2023-2024 | 2137/Bol.MD | 25/08/2023 | 24/10/2023 | M. S. ENTERPRISE | 45.52 | 12.28 | 26.98 | 30
7 | BIRBHUM | Nalhati - II | Bolpur Mechanical | Nawapara Piped Water Supply Scheme | SM/13479 | New | Supply and Delivery of Volage correction device, Cetrifugal Pumping Machineries and allied accessories for Nawapara PWSS, (Block- Nalhati - II) under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000521/2024-2025 | 3780/BOL.MD | 12/09/2024 | 12/10/2024 | S.K.ELECTRICALS | 33.77 | 0 | 0 | 0
Total | [13 empty] | 1022.66 | 14.58 | 1.43