## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Dubrajpur | Birbhum Division | Modapa Piped Water Supply Scheme. | SM/13517 | New | Submission of Wayleave/Track crossing proposal in IR-RBCS station from Dubrajpur to Chinpai (38-39) KM |  |  | BILL/00166/2024-2025 | BP-2024-25-67 | 30/05/2024 |  | EASTERN RAILWAY | 5.35 | 0 | 0 | null
2 | BIRBHUM | Dubrajpur | Birbhum Division | Modapa Piped Water Supply Scheme. | SM/13517 | New | Different works related to water supply scheme at MODAPA & its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE3 | ORD/000063/2023-2024 | 1303/BHM | 19/04/2023 | 14/01/2024 | J.P.ENTERPRISE | 280.53 | 34.2 | 12.19 | 58
3 | BIRBHUM | Dubrajpur | Birbhum Division | Modapa Piped Water Supply Scheme. | SM/13517 | New | Material Requisition To Resource Division |  |  | RTOR000080/2022-2023 | 1399/BHM | 24/04/2023 |  | Resource Division | 12.63 | 0 | 0 | 0
4 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Modapa Piped Water Supply Scheme. | SM/13517 | New | WBSEDCL QUOIT ION FOR MODAPA PUMP HOUSE NO I |  |  | BILL/01826/2023-2024 | BP-23-24-263 | 06/02/2024 |  | WBSEDCL | 3.59 | 0 | 0 | 0
5 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Modapa Piped Water Supply Scheme. | SM/13517 | New | WBSEDL QUOTATION FOR MODAPA PUMP HOUSEN NO II |  |  | BILL/01827/2023-2024 | BP-23-24-262 | 06/02/2024 |  | WBSEDCL | 4.42 | 0 | 0 | 0
6 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Modapa Piped Water Supply Scheme. | SM/13517 | New | Providing Electro-mechanical accessories and others for Modapa & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/001381/2023-2024 | 2242/BOL.MD | 13/09/2023 | 12/11/2023 | SWAPAN ENTERPRISE | 10.16 | 5.81 | 57.2 | 90
Total | [13 empty] | 316.69 | 40.01 | 12.63