## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Dubrajpur | Birbhum Division | Kukutia piped water supply scheme. | SM/13601 | New | Sinking of 250 mm. X 200 mm Dia deep tubewell , construction of 150 CuM capacity O.H.R.with soil Investigation, 100 CuM CWR, Pump room/ Chlorine room with/without sanitary arrangements( different size),and laying of Rising main, Laying distribution with FHTC and different works related to KUKUTIA & its adjoining mouzas water supply scheme within Dubrajpur Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE | JE3 | ORD/000116/2024-2025 | 2182/BHM | 06/08/2024 | 06/08/2025 | SARAFAT KHAN | 328.94 | 0 | 0 | 0
2 | BIRBHUM | Dubrajpur | Birbhum Division | Kukutia piped water supply scheme. | SM/13601 | New | Material Requisition To Resource Division |  |  | RTOR000031/2024-2025 | 2487/BHM | 03/09/2024 |  | Resource Division | 8.26 | 0 | 0 | 0
3 | BIRBHUM | Dubrajpur | Birbhum Division | Kukutia piped water supply scheme. | SM/13601 | New | Material Requisition To Resource Division |  |  | RTOR000076/2022-2023 | 1394/BHM | 24/04/2023 |  | Resource Division | 67.88 | 0 | 0 | 0
4 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Kukutia piped water supply scheme. | SM/13601 | New | Providing Electro-mechanical accessories and others for Kukutia & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000936/2023-2024 | 3393/Bol.MD | 17/10/2023 | 15/01/2024 | S.K.ELECTRICALS | 52.82 | 0 | 0 | 0
Total | [13 empty] | 457.91 | 0 | 0