## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Sainthia | Birbhum Division | UTTAR BANGAON PIPED WATER SUPPLY SCHEME. | SM/13626 | New | Different works related to water supply scheme at ABHIRAMPUR, BEHIRA, SAMSA & UTTAR BANGAON and its adjoining mouzas water supply scheme within SAINTHIA Block under Birbhum Division, PHE Dte. | AE | JE | ORD/000082/2023-2024 | 1437/BHM | 25/04/2023 | 20/01/2024 | ASHOK KUMAR GHOSH | 1446.74 | 0 | 0 | 35
2 | BIRBHUM | Sainthia | Birbhum Division | UTTAR BANGAON PIPED WATER SUPPLY SCHEME. | SM/13626 | New | Material Requisition To Resource Division |  |  | RTOR000054/2022-2023 | 1369/BHM | 24/04/2023 |  | Resource Division | 37.66 | 0 | 0 | 0
3 | BIRBHUM | Sainthia | Bolpur Mechanical | UTTAR BANGAON PIPED WATER SUPPLY SCHEME. | SM/13626 | New | WBSEDCL QUOTATION FOR UTTAR BANGAON P H NO.I WS SCHEME |  |  | BILL/01473/2023-2024 | BP-23-24-199 | 12/12/2023 |  | WBSEDCL | 7.29 | 0 | 0 | 0
4 | BIRBHUM | Sainthia | Bolpur Mechanical | UTTAR BANGAON PIPED WATER SUPPLY SCHEME. | SM/13626 | New | WBSEDCL QUOTATION FOR UTTAR BANGAOUN WS SCHEME |  |  | BILL/02140/2023-2024 | BP-23-24-303 | 15/03/2024 |  | WBSEDCL | 6.69 | 0 | 0 | 0
5 | BIRBHUM | Sainthia | Bolpur Mechanical | UTTAR BANGAON PIPED WATER SUPPLY SCHEME. | SM/13626 | New | Providing Electro-mechanical accessories and others for Uttar Bangaon & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000388/2023-2024 | 1927/Bol.MD | 11/08/2023 | 10/10/2023 | P. K. ENGINEERING | 27.89 | 0 | 0 | 0
Total | [13 empty] | 1526.27 | 0 | 0