## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar - II | Birbhum Division | Beluti Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division | SM/13634 | New | Different works related to Water Supply Scheme at BELUTI & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE3 | ORD/000536/2022-2023 | 673/BHM | 01/03/2023 | 26/11/2023 | ESCON INDIA | 208.6 | 102.73 | 49.25 | 30
2 | BIRBHUM | Mayureswar - II | Birbhum Division | Beluti Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division | SM/13634 | New | Preparation & Submission of DPR for (Beluti) Water Supply Scheme under Mayureswar-II Development Block. | AE | JE3 | ORD/000562/2022-2023 | 161/RSD | 20/04/2022 | 04/06/2022 | ENVIROTECH SOLUTIONS | 2.15 | 1.97 | 91.6 | 100
3 | BIRBHUM | Mayureswar - II | Birbhum Division | Beluti Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division | SM/13634 | New | Material Requisition To Resource Division |  |  | RTOR000094/2023-2024 | 1486/BHM | 25/04/2023 |  | Resource Division | 2.93 | 0 | 0 | 0
4 | BIRBHUM | Mayureswar - II | Birbhum Division | Beluti Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division | SM/13634 | New | Material Requisition To Resource Division |  |  | RTOR000208/2023-2024 | 203/BHM | 22/01/2024 |  | Resource Division | 2.56 | 0 | 0 | 0
5 | BIRBHUM | Mayureswar - II | Bolpur Mechanical | Beluti Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division | SM/13634 | New | WBSEDCL QUOTATION FOR RBELUTI P H NO.II WS SCHEME |  |  | BILL/01487/2023-2024 | BP-23-24-198 | 19/12/2023 |  | WBSEDCL | 2.91 | 0 | 0 | 0
6 | BIRBHUM | Mayureswar - II | Bolpur Mechanical | Beluti Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division | SM/13634 | New | WBSEDCL QUOITATION FOR BELUTI PH NO-I |  |  | BILL/01837/2023-2024 | BP-23-24-267 | 07/02/2024 |  | WBSEDCL | 8.05 | 0 | 0 | 0
7 | BIRBHUM | Mayureswar - II | Bolpur Mechanical | Beluti Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division | SM/13634 | New | Providing Electro-mechanical accessories and others for Beluti PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000845/2023-2024 | 3284/Bol.MD | 29/09/2023 | 28/11/2023 | DEY ENTERPRISE | 43.64 | 10.29 | 23.57 | 60
Total | [13 empty] | 270.84 | 114.99 | 42.46