## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Kendangal Piped Water Supply Scheme. | SM/13642 | New | Different works related to water supply scheme at IKSHUDHARA, KANKALITALA, KASBA & KENDANGAL Piped Water Supply Scheme within BOLPUR-SRINIKETAN Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE4 | ORD/000402/2023-2024 | 4139/BHM | 18/10/2023 | 14/07/2024 | M/S TAPAS KUMAR CHAKRABORTY | 2684.99 | 0 | 0 | 25
2 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Kendangal Piped Water Supply Scheme. | SM/13642 | New | Material Requisition To Resource Division |  |  | RTOR000088/2022-2023 | 1360/BHM | 24/04/2023 |  | Resource Division | 16.65 | 0 | 0 | 0
3 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Kendangal Piped Water Supply Scheme. | SM/13642 | New | NEW SERVICE CONNECTION AT KENDRADANGAL WATER SUPPLY SCHEME. |  |  | BILL/00437/2024-2025 | BP-2024-25-140 | 06/08/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.31 | 0 | 0 | null
4 | BIRBHUM | Bolpur Sriniketan | Central Drilling | Kendangal Piped Water Supply Scheme. | SM/13642 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 24044.7 | 0 | 0