## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mohammad Bazar | Birbhum Division | Sadanandapur piped water supply scheme. | SM/13648 | New | Different works related to water supply scheme at SADANANDPUR & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE(HQ) | JE | ORD/000151/2023-2024 | 2019/BHM | 06/06/2023 | 02/03/2024 | NABIN DEBNATH | 344.07 | 75.4 | 21.91 | 80
2 | BIRBHUM | Mohammad Bazar | Birbhum Division | Sadanandapur piped water supply scheme. | SM/13648 | New | Material Requisition To Resource Division |  |  | RTOR000091/2023-2024 | 1548/BHM | 26/04/2023 |  | Resource Division | 9.67 | 0 | 0 | 0
3 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | Sadanandapur piped water supply scheme. | SM/13648 | New | WBSEDCL QUOTATION FOR SADANANDAPUR PH NO-1 |  |  | BILL/01570/2023-2024 | BP-23-24-224 | 15/01/2024 |  | WBSEDCL | 0.31 | 0 | 0 | 0
4 | BIRBHUM | Mohammad Bazar | Bolpur Mechanical | Sadanandapur piped water supply scheme. | SM/13648 | New | Providing Electro-mechanical accessories and others for SADANANDAPUR piped water supply scheme, Md. Bazar block, under Bolpur Mechanical Division PHE Dte. | Driller in Charge | Junior Engineer | ORD/000295/2023-2024 | 1500/Bol.MD | 17/07/2023 | 15/09/2023 | SATYAJIT GHOSH | 27.88 | 20.74 | 74.4 | 70
Total | [13 empty] | 381.92 | 96.14 | 25.17