## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar - I | Birbhum Division | Taloan Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/13653 | New | Different works related to water supply scheme at TALWAN & its adjoining mouzas water supply scheme within Mayureswar-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. (3rd Call) | AE | JE2 | ORD/000476/2023-2024 | 601/BHM | 09/02/2024 | 05/11/2024 | PRALAY ROY | 309.43 | 0 | 0 | 0
2 | BIRBHUM | Mayureswar - I | Birbhum Division | Taloan Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/13653 | New | Continuation Work Order for Preparation & Submission of DPR for (Talowan) Water Supply Scheme under Mayureswar-I Development Block. | AE | JE1 | ORD/000637/2022-2023 | 264/RSD | 29/07/2022 | 27/10/2022 | ENVIROTECH SOLUTIONS | 3.58 | 1.57 | 43.98 | 100
3 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | Taloan Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. | SM/13653 | New | Providing Electro-mechanical accessories and others for Taloan PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000722/2023-2024 | 3471/Bol.MD | 07/11/2023 | 06/01/2024 | QUAZI NOZRUL ISLAM | 43.81 | 10.89 | 24.86 | 40
Total | [13 empty] | 356.82 | 12.46 | 3.49