## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat - II | Birbhum Division | Khamedda Piped Water Supply Scheme | SM/13980 | New | Different works related to water supply scheme at Madhupur, Khamedda & Bara-Karttikchungri and its adjoining mouzas water supply scheme within Rampurhat-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte.(2nd Call) | AE | JE3 | ORD/000395/2023-2024 | 4163/BHM | 30/10/2023 | 26/07/2024 | M/S ASHA CONSTRUCTION | 1089.94 | 0 | 0 | 0
2 | BIRBHUM | Rampurhat - II | Birbhum Division | Khamedda Piped Water Supply Scheme | SM/13980 | New | Continuation Work Order for Preparation & Submission of DPR for (Khamedda) Water Supply Scheme under Rampurhat-II Development Block. | AE | JE2 | ORD/000636/2022-2023 | 262/RSD | 27/07/2022 | 10/09/2022 | ECO CARE | 4.73 | 2.19 | 46.26 | 100
3 | BIRBHUM | Rampurhat - II | Birbhum Division | Khamedda Piped Water Supply Scheme | SM/13980 | New | Material Requisition To Resource Division |  |  | RTOR000087/2023-2024 | 1583/BHM | 26/04/2023 |  | Resource Division | 26.44 | 0 | 0 | 0
4 | BIRBHUM | Rampurhat - II | Birbhum Division | Khamedda Piped Water Supply Scheme | SM/13980 | New | Material Requisition To Resource Division |  |  | RTOR000230/2023-2024 | 225/BHM | 24/01/2024 |  | Resource Division | 3.08 | 0 | 0 | 0
5 | BIRBHUM | Rampurhat - II | Bolpur Mechanical | Khamedda Piped Water Supply Scheme | SM/13980 | New | Quotation for new service connection at Khamedda PWSS P.H No-I (Block-Rampurhat - II), Margram CCC, WBSEDCL |  |  | BILL/00123/2024-2025 | BP-2024-2025-61 | 05/06/2024 |  | WBSEDCL | 2.75 | 0 | 0 | null
6 | BIRBHUM | Rampurhat - II | Bolpur Mechanical | Khamedda Piped Water Supply Scheme | SM/13980 | New | Providing Electro-mechanical accessories and others for Khameda PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000471/2023-2024 | 2224/Bol.MD | 12/09/2023 | 11/11/2023 | HINDOL ROY | 45.7 | 21.33 | 46.69 | 50
Total | [13 empty] | 1172.63 | 23.52 | 2.01