## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nalhati - II | Birbhum Division | Shitalgram Piped Water Supply Scheme | SM/14087 | New | Different works works related to water supply scheme at Atkulia, Shitalgram & its adjoining mouzas water supply scheme within NALHATI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE | JE2 | ORD/000205/2023-2024 | 3236/BHM | 25/07/2023 | 20/04/2024 | MS S CHOUDHURY | 1020.41 | 70.37 | 6.9 | 30
2 | BIRBHUM | Nalhati - II | Birbhum Division | Shitalgram Piped Water Supply Scheme | SM/14087 | New | Preparation and submission of DPR for (Shitalgram) Water Supply Scheme under Nalhati-II Development Block. | AE | JE2 | ORD/000760/2022-2023 | 233/AE/NSD | 21/04/2022 | 05/06/2022 | MS SOBHA AND CO | 4.14 | 2.07 | 50 | 100
3 | BIRBHUM | Nalhati - II | Birbhum Division | Shitalgram Piped Water Supply Scheme | SM/14087 | New | Material Requisition To Resource Division |  |  | RTOR000174/2023-2024 | 2175/BHM | 23/06/2023 |  | Resource Division | 19.69 | 0 | 0 | 0
4 | BIRBHUM | Nalhati - II | Bolpur Mechanical | Shitalgram Piped Water Supply Scheme | SM/14087 | New | WBSEDCL QUOTATION FOR SHITALGRAM WS SCHEME |  |  | BILL/01605/2023-2024 | BP-23-24-235 | 29/01/2024 |  | WBSEDCL | 3.62 | 0 | 0 | 0
5 | BIRBHUM | Nalhati - II | Bolpur Mechanical | Shitalgram Piped Water Supply Scheme | SM/14087 | New | Providing Electro-mechanical accessories and others for Shitalgram PWSS at Nalhati - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000700/2023-2024 | 2109/Bol.MD | 22/08/2023 | 21/10/2023 | HINDOL ROY | 45.44 | 9.8 | 21.57 | 40
Total | [13 empty] | 1093.31 | 82.25 | 7.52