## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar - II | Birbhum Division | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Different works related to Water Supply Scheme at PRAYAGPUR & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE2 | ORD/000276/2023-2024 | 3596/BHM | 21/08/2023 | 17/05/2024 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 516.3 | 0 | 0 | 40
2 | BIRBHUM | Mayureswar - II | Birbhum Division | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Continuation Work Order for Preparation & Submission of DPR for (PRAYAGPUR) Water Supply Scheme (Part-A) under Mayureswar-II Development Block. | AE | JE3 | ORD/000842/2022-2023 | 333/RSD | 08/09/2022 | 23/10/2022 | ENVIROTECH SOLUTIONS | 3.22 | 2.28 | 70.71 | 100
3 | BIRBHUM | Mayureswar - II | Birbhum Division | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Continuation Work Order for Preparation & Submission of DPR for (PRAYAGPUR) Water Supply Scheme (Part-B) under Mayureswar-II Development Block. | AE | JE3 | ORD/000843/2022-2023 | 437/RSD | 25/11/2022 | 09/01/2023 | ENVIROTECH SOLUTIONS | 2.5 | 0.06 | 2.43 | 100
4 | BIRBHUM | Mayureswar - II | Birbhum Division | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Material Requisition To Resource Division |  |  | RTOR000024/2023-2024 | 1444/BHM | 25/04/2023 |  | Resource Division | 36.79 | 0 | 0 | 0
5 | BIRBHUM | Mayureswar - II | Birbhum Division | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Material Requisition To Resource Division |  |  | RTOR000215/2023-2024 | 231/BHM | 24/01/2024 |  | Resource Division | 5.61 | 0 | 0 | 0
6 | BIRBHUM | Mayureswar - II | Bolpur Mechanical | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Providing and Installation of Submersible pumping Machineries at newly sunk Tube Well and allieds works at Prayagpur Piped Water Supply Scheme, Block-Mayureswar-II under Bolpur Mechanical Division, P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/000509/2024-2025 | 3756/Bol.MD | 12/09/2024 | 12/10/2024 | M/S P.P ELECTRICALS | 25.25 | 0 | 0 | 0
7 | BIRBHUM | Mayureswar - II | Bolpur Mechanical | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Providing Electro-mechanical accessories and others for Prayagpur PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000839/2023-2024 | 3278/Bol.MD | 29/09/2023 | 28/11/2023 | ORIENTAL ENGINEERING CO. | 55.59 | 0 | 0 | 0
8 | BIRBHUM | Mayureswar - II | Bolpur Mechanical | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division | SM/14088 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Prayagpur PWSS under Mayureswar - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte | Assistant Engineer-III | Junior Engineer | ORD/001244/2023-2024 | 529/BOL.MD | 14/03/2024 | 13/05/2024 | SWAPAN ENTERPRISE | 7.62 | 0 | 0 | 0
Total | [13 empty] | 652.87 | 2.34 | 0.36