## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar - I | Birbhum Division | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division | SM/14119 | New | Different works related to water supply scheme at KANKSA & its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE2 | ORD/000089/2023-2024 | 1879/BHM | 31/05/2023 | 25/02/2024 | PRANAB KUMAR GHOSH | 229 | 51.98 | 22.7 | 65
2 | BIRBHUM | Mayureswar - I | Birbhum Division | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division | SM/14119 | New | Continuation Work Order for Preparation & Submission of DPR for (Kanska) Water Supply Scheme under Mayureswar-I Development Block. | AE | JE1 | ORD/000631/2022-2023 | 230/RSD | 27/06/2022 | 25/09/2022 | ENVIROTECH SOLUTIONS | 2.86 | 1.16 | 40.64 | 100
3 | BIRBHUM | Mayureswar - I | Birbhum Division | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division | SM/14119 | New | Material Requisition To Resource Division |  |  | RTOR000021/2023-2024 | 1447/BHM | 25/04/2023 |  | Resource Division | 5.45 | 0 | 0 | 0
4 | BIRBHUM | Mayureswar - I | Birbhum Division | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division | SM/14119 | New | Material Requisition To Resource Division |  |  | RTOR000203/2023-2024 | 206/BHM | 22/01/2024 |  | Resource Division | 3.91 | 0 | 0 | 0
5 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division | SM/14119 | New | WBSEDCL QUOTATION FOR KANKSA P H NO -2 WS SCHEME |  |  | BILL/01438/2023-2024 | BP-23-24-178 | 07/12/2023 |  | WBSEDCL | 3.82 | 0 | 0 | 0
6 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division | SM/14119 | New | WBSEDCL QUOTATION FOR PURBA KANKSA P H NO II WS SCHEME |  |  | BILL/01789/2023-2024 | BP-23-24-256 | 06/02/2024 |  | WBSEDCL | 5.76 | 0 | 0 | 0
7 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division | SM/14119 | New | Supplly & delivery of pumping machinery Kanksa water supply scheme Block- Mayureswar-I under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000004/2024-2025 | 690./AE-III | 08/04/2024 | 22/04/2024 | GOENKA ENTERPRISE | 1.48 | 1.12 | 76 | 100
8 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division | SM/14119 | New | Providing Electro-mechanical accessories and others for Kanksa PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000524/2023-2024 | 2155/Bol.MD | 28/08/2023 | 27/10/2023 | GOENKA ENTERPRISE | 44.03 | 11.31 | 25.68 | 50
Total | [13 empty] | 296.3 | 65.58 | 22.13