## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Labpur | Birbhum Division | MONACHITURA PIPED WATER SUPPLY SCHEME | SM/14450 | New | Preparation & Submission of Detail Project Report (DPR) for MONACHITURA Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte. | AE | JE3 | ORD/001135/2021-2022 | 100/BSD | 15/03/2022 | 11/09/2022 | APEX ENGINEERING | 4.92 | 2.19 | 44.56 | 100
2 | BIRBHUM | Labpur | Central Drilling | MONACHITURA PIPED WATER SUPPLY SCHEME | SM/14450 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21344.69 | 2.19 | 0.01