## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Albandha Piped Water Supply Scheme. | SM/14533 | New | Different works related to water supply scheme at ALBANDHA, BERGRAM & BIDYADHARPUR Piped Water Supply Scheme within BOLPUR-SRINIKETAN Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. (2nd Call) | AE | JE4 | ORD/000387/2023-2024 | 4146/BHM | 19/10/2023 | 15/07/2024 | AMAL DUTTA ROY | 1648.21 | 0 | 0 | 12
2 | BIRBHUM | Bolpur Sriniketan | Birbhum Division | Albandha Piped Water Supply Scheme. | SM/14533 | New | Material Requisition To Resource Division |  |  | RTOR000104/2023-2024 | 1547/BHM | 26/04/2023 |  | Resource Division | 219.35 | 0 | 0 | 0
3 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Albandha Piped Water Supply Scheme. | SM/14533 | New | WBSEDCL QUOTATION FOR ALBANDHA WS SCHEME |  |  | BILL/01591/2023-2024 | BP-23-24-221 | 15/01/2024 |  | WBSEDCL | 5.28 | 0 | 0 | 0
4 | BIRBHUM | Bolpur Sriniketan | Bolpur Mechanical | Albandha Piped Water Supply Scheme. | SM/14533 | New | Providing Electro-mechanical accessories and others for Albandha & Adjoining moujas water supply scheme at Bolpur Sriniketan Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000478/2023-2024 | 2238/BOL.MD. | 13/09/2023 | 12/12/2023 | DEY ENTERPRISE | 73.35 | 17.5 | 23.86 | 50
5 | BIRBHUM | Bolpur Sriniketan | Central Drilling | Albandha Piped Water Supply Scheme. | SM/14533 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 23285.94 | 17.5 | 0.08