## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Nalhati - I | Birbhum Division | Banior Piped Water Supply Scheme. | SM/14688 | New | Different works related to water supply scheme at BANIOR & its adjoining mouzas water supply scheme within NALHATI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE1 | ORD/000332/2023-2024 | 3777/BHM | 08/09/2023 | 04/06/2024 | TUSHAR KANTI GHOSH | 1573.21 | 0 | 0 | 0
2 | BIRBHUM | Nalhati - I | Birbhum Division | Banior Piped Water Supply Scheme. | SM/14688 | New | Material Requisition To Resource Division |  |  | RTOR000163/2023-2024 | 1625/BHM | 28/04/2023 |  | Resource Division | 654.06 | 0 | 0 | 0
3 | BIRBHUM | Nalhati - I | Bolpur Mechanical | Banior Piped Water Supply Scheme. | SM/14688 | New | Supply & Installation of High lift pumping machineries and other allied works for Banior piped water supply scheme within Nalhati-I block, under Bolpur Mechanical Division PHE Dte.. | Assistant Engineer-III | Junior Engineer | ORD/000919/2023-2024 | 3557/BOL.MD | 04/12/2023 | 03/03/2024 | MACHINE SUPPLIERS SYNDUCATE (P) LTD. | 95.52 | 0 | 0 | 0
4 | BIRBHUM | Nalhati - I | Bolpur Mechanical | Banior Piped Water Supply Scheme. | SM/14688 | New | Supply & Installation of Low lift pumping machineries and other allied works for Banior piped water supply scheme within Nalhati-I block, under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000930/2023-2024 | 3560/BOL.MD | 04/12/2023 | 03/03/2024 | QUAZI NOZRUL ISLAM | 74.52 | 29.09 | 39.03 | 30
Total | [13 empty] | 2397.31 | 29.09 | 1.21