## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Mayureswar - I | Birbhum Division | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT | SM/14894 | New | Different works related to water supply scheme at RAUTGARA & its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE1 | ORD/000569/2022-2023 | 902/BHM | 22/03/2023 | 17/12/2023 | PULAK KUMAR PAL | 173.47 | 113.31 | 65.32 | 70
2 | BIRBHUM | Mayureswar - I | Birbhum Division | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT | SM/14894 | New | Continuation Work Order for Preparation & Submission of DPR for (Rautgara) Water Supply Scheme under Mayureswar-I Development Block. | AE | JE1 | ORD/000633/2022-2023 | 236/RSD | 05/07/2022 | 03/10/2022 | ENVIROTECH SOLUTIONS | 2.15 | 0.95 | 44.4 | 100
3 | BIRBHUM | Mayureswar - I | Birbhum Division | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT | SM/14894 | New | Material Requisition To Resource Division |  |  | RTOR000027/2023-2024 | 1567/BHM | 26/04/2023 |  | Resource Division | 4.49 | 0 | 0 | 0
4 | BIRBHUM | Mayureswar - I | Birbhum Division | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT | SM/14894 | New | Material Requisition To Resource Division |  |  | RTOR000200/2023-2024 | 196/BHM | 22/01/2024 |  | Resource Division | 0.12 | 0 | 0 | 0
5 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT | SM/14894 | New | WBSEDCL QUOTATION FOR RAUTGARA PUMP HOUSE NO-I& II |  |  | BILL/02119/2023-2024 | BP-2023-24-291 | 06/03/2024 |  | WBSEDCL | 2.78 | 0 | 0 | 0
6 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT | SM/14894 | New | Supply and Delivery of Pumping Machinery for Routgara water supply scheme Block Mayureswar ¿ I under Bolpur Mechanical Division PHE. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000196/2024-2025 | 946./AE-III | 27/06/2024 | 04/07/2024 | M. S. ENTERPRISE | 1.49 | 0.75 | 50 | 100
7 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT | SM/14894 | New | Providing Electro-mechanical accessories and others for Rautgara PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000351/2023-2024 | 1748/Bol.MD | 27/07/2023 | 25/09/2023 | M. S. ENTERPRISE | 45.04 | 17.21 | 38.21 | 70
8 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT | SM/14894 | New | Supply & delivery of Submersible Cable acceessories for Routgara Piped water supply scheme. under Bolpur Mechanical Division, PHE. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000352/2024-2025 | 1183./AE-III | 09/08/2024 | 19/08/2024 | RAJIB GHOSH | 0.99 | 0 | 0 | 0
9 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT | SM/14894 | New | Supply & delivery of submersible cable accessories at Routgara Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000430/2024-2025 | 1296./AE-III | 27/08/2024 | 03/09/2024 | RAJIB GHOSH | 2.52 | 0 | 0 | 0
10 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT | SM/14894 | New | Supply & delivery of different electrical accessories at Routgara Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000460/2024-2025 | 1308./AE-III | 28/08/2024 | 04/09/2024 | TAPAN ENTERPRISE | 2.95 | 0 | 0 | 0
11 | BIRBHUM | Mayureswar - I | Bolpur Mechanical | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT | SM/14894 | New | Supply and Delivery of Sub-Mersible Pump Controllers for Routgara water supply scheme under Bolpur Mechanical Division, PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000528/2024-2025 | 1453./AE-III | 09/09/2024 | 16/09/2024 | M/S. YOUTH ENGINEERS' ENTERPRISE | 2.86 | 0 | 0 | 0
Total | [13 empty] | 238.87 | 132.22 | 55.35