## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat - II | Birbhum Division | HANSAN PIPED WATER SUPPLY SCHEME | SM/14900 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 250 CuM OHR , Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at HANSAN & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE3 | ORD/000114/2024-2025 | 2179/BHM | 06/08/2024 | 06/08/2025 | RADIANT | 490.17 | 0 | 0 | 0
2 | BIRBHUM | Rampurhat - II | Birbhum Division | HANSAN PIPED WATER SUPPLY SCHEME | SM/14900 | New | Continuation Work Order for Preparation & Submission of DPR for (HANSAN) Water Supply Scheme (Part-A) under Rampurhat-II Development Block. | AE | JE3 | ORD/000790/2022-2023 | 326/RSD | 08/09/2022 | 23/10/2022 | ECO CARE | 3.05 | 0.12 | 3.78 | 100
3 | BIRBHUM | Rampurhat - II | Birbhum Division | HANSAN PIPED WATER SUPPLY SCHEME | SM/14900 | New | Continuation Work Order for Preparation & Submission of DPR for (HANSAN) Water Supply Scheme (Part-B) under Rampurhat-II Development Block. | AE | JE3 | ORD/000799/2022-2023 | 426/RSD | 04/11/2022 | 19/12/2022 | ECO CARE | 2.91 | 2.69 | 92.47 | 100
4 | BIRBHUM | Rampurhat - II | Birbhum Division | HANSAN PIPED WATER SUPPLY SCHEME | SM/14900 | New | Material Requisition To Resource Division |  |  | RTOR000028/2023-2024 | 1520/BHM | 26/04/2023 |  | Resource Division | 25.75 | 0 | 0 | 0
5 | BIRBHUM | Rampurhat - II | Birbhum Division | HANSAN PIPED WATER SUPPLY SCHEME | SM/14900 | New | Material Requisition To Resource Division |  |  | RTOR000042/2024-2025 | 2485/BHM | 03/09/2024 |  | Resource Division | 11.9 | 0 | 0 | 0
6 | BIRBHUM | Rampurhat - II | Bolpur Mechanical | HANSAN PIPED WATER SUPPLY SCHEME | SM/14900 | New | Supply & delivery of Sub-Mersible Pump Controllers for Hasan water supply scheme (Block- Rampurhat - II) under Bolpur Mechanical Division, PHE Dte. |  |  | ORD/000402/2024-2025 | 1295./AE-III | 27/08/2024 | 03/09/2024 | SWAPAN BANERJEE | 2.84 | 0 | 0 | 0
7 | BIRBHUM | Rampurhat - II | Bolpur Mechanical | HANSAN PIPED WATER SUPPLY SCHEME | SM/14900 | New | Providing Electro-mechanical accessories and others for Hansan PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000476/2023-2024 | 2229/Bol.MD | 12/09/2023 | 11/11/2023 | P. K. ENGINEERING | 44.33 | 0 | 0 | 0
8 | BIRBHUM | Rampurhat - II | Bolpur Mechanical | HANSAN PIPED WATER SUPPLY SCHEME | SM/14900 | New | Supply & delivery of Main Swich, Change over switch,Busbar for Hasan water supply scheme (Block- Suri - I) under Bolpur Mechanical Division, PHE Dte. " |  |  | ORD/000529/2024-2025 | 1454./AE-III | 09/09/2024 | 16/09/2024 | SATYAJIT GHOSH | 0 | 0 | NAN | 0
9 | BIRBHUM | Rampurhat - II | Bolpur Mechanical | HANSAN PIPED WATER SUPPLY SCHEME | SM/14900 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Hansan PWSS under Rampurhat - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte | Assistant Engineer-III | Junior Engineer | ORD/001243/2023-2024 | 522/BOL.MD | 14/03/2024 | 13/05/2024 | KAMAKHYA ENTERPRISE | 7.62 | 0 | 0 | 0
Total | [13 empty] | 588.56 | 2.8 | 0.48