## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat - II | Birbhum Division | PARKUTA PIPED WATER SUPPLY SCHEME | SM/14959 | New | Different works related to water supply scheme at PARKUTA & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | AE | JE2 | ORD/000068/2023-2024 | 1341/BHM | 20/04/2023 | 17/10/2023 | KAZI EMDADUL HAQUE | 118.27 | 15.13 | 12.79 | 90
2 | BIRBHUM | Rampurhat - II | Birbhum Division | PARKUTA PIPED WATER SUPPLY SCHEME | SM/14959 | New | Continuation Work Order for Preparation & Submission of DPR for (Perkuta) Water Supply Scheme under Rampurhat-II Development Block. | AE | JE2 | ORD/000639/2022-2023 | 281/RSD | 24/08/2022 | 08/10/2022 | ECO CARE | 2.18 | 0.81 | 36.98 | 100
3 | BIRBHUM | Rampurhat - II | Birbhum Division | PARKUTA PIPED WATER SUPPLY SCHEME | SM/14959 | New | Material Requisition To Resource Division |  |  | RTOR000023/2023-2024 | 1445/BHM | 25/04/2023 |  | Resource Division | 7.01 | 0 | 0 | 0
4 | BIRBHUM | Rampurhat - II | Birbhum Division | PARKUTA PIPED WATER SUPPLY SCHEME | SM/14959 | New | Material Requisition To Resource Division |  |  | RTOR000224/2023-2024 | 221/BHM | 24/01/2024 |  | Resource Division | 2.46 | 0 | 0 | 0
5 | BIRBHUM | Rampurhat - II | Bolpur Mechanical | PARKUTA PIPED WATER SUPPLY SCHEME | SM/14959 | New | wbsedcl quotation money for parkuta pwss |  |  | BILL/01430/2023-2024 | BP-23-24-150 | 04/12/2023 |  | WBSEDCL | 3.99 | 0 | 0 | 0
6 | BIRBHUM | Rampurhat - II | Bolpur Mechanical | PARKUTA PIPED WATER SUPPLY SCHEME | SM/14959 | New | WBSEDCL QUOTATION FOR PARKUTA P H NO.II WS SCHEME |  |  | BILL/01875/2023-2024 | BP-23-24-279 | 20/02/2024 |  | WBSEDCL | 4.98 | 0 | 0 | 0
7 | BIRBHUM | Rampurhat - II | Bolpur Mechanical | PARKUTA PIPED WATER SUPPLY SCHEME | SM/14959 | New | Supply and Delivery of Sub-Mersible Pumping Machineries inconection with Providing Electro-mechanical accessories and others for Parkuta PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000006/2024-2025 | 686./AE-III | 08/04/2024 | 22/04/2024 | SINHA ELECTRICALS | 1.74 | 0.63 | 36 | 100
8 | BIRBHUM | Rampurhat - II | Bolpur Mechanical | PARKUTA PIPED WATER SUPPLY SCHEME | SM/14959 | New | Providing Electro-mechanical accessories and others for Parkuta PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000473/2023-2024 | 2226/Bol.MD | 12/09/2023 | 11/11/2023 | SINHA ELECTRICALS | 45.18 | 18.95 | 41.94 | 30
Total | [13 empty] | 185.81 | 35.51 | 19.11