## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Labpur | Birbhum Division | MASTALI PIPED WATER SUPPLY SCHEME | SM/16275 | New | Different works related to water supply scheme at MASTALI Piped Water Supply Scheme (TSM/017207) within Labpur Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. (3rd Call) | AE | JE1,JE3 | ORD/000473/2023-2024 | 523/BHM | 05/02/2024 | 01/11/2024 | PREMANANDA ROY BISWAS | 302.55 | 0 | 0 | 20
2 | BIRBHUM | Labpur | Birbhum Division | MASTALI PIPED WATER SUPPLY SCHEME | SM/16275 | New | Continuation work Order for "Preparation & Submission of Detail Project Report (DPR) for MASTALI Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | AE | JE3 | ORD/000657/2022-2023 | 172/BSD | 29/04/2022 | 24/04/2023 | APEX ENGINEERING | 3.16 | 1.29 | 40.85 | 100
3 | BIRBHUM | Labpur | Bolpur Mechanical | MASTALI PIPED WATER SUPPLY SCHEME | SM/16275 | New | New power connection at Mastali PWSS(P/H-I) |  |  | BILL/00565/2024-2025 | BP-24-25-162 | 27/08/2024 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.35 | 0 | 0 | null
4 | BIRBHUM | Labpur | Bolpur Mechanical | MASTALI PIPED WATER SUPPLY SCHEME | SM/16275 | New | Hiring of Car (B.S.-IV) WB-53 C 3045. for the Office of the Assistant Engineer- III, Central Mechanical Division, PHE. Dte. Under Bolpur Mechanical Division, P.H.E. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000210/2024-2025 | 748./AE-III | 29/04/2024 | 27/06/2024 | RAJIB GHOSH | 0.28 | 0 | 0 | 0
5 | BIRBHUM | Labpur | Bolpur Mechanical | MASTALI PIPED WATER SUPPLY SCHEME | SM/16275 | New | Hiring of Car (B.S.-IV) WB-53 C 3045. for the Office of the Assistant Engineer- III, Central Mechanical Division, PHE. Dte. Under Bolpur Mechanical Division, P.H.E. Dte. | Assistant Engineer-III | Junior Engineer | ORD/000331/2024-2025 | 920/AE-III | 24/06/2024 | 24/09/2024 | RAJIB GHOSH | 0.44 | 0 | 0 | 0
6 | BIRBHUM | Labpur | Bolpur Mechanical | MASTALI PIPED WATER SUPPLY SCHEME | SM/16275 | New | Hiring of Luxury Car (Diesel) for the office of the Assistant Engineer, Bolpur Mechanical Division. PHE. Dte. | Assistant Engineer (HQ) | Junior Engineer | ORD/001382/2023-2024 | 3397/BOL.MD | 31/10/2023 | 29/02/2024 | RAJIB GHOSH | 0.57 | 1.54 | 267.84 | 100
7 | BIRBHUM | Labpur | Bolpur Mechanical | MASTALI PIPED WATER SUPPLY SCHEME | SM/16275 | New | Hiring of Car (B.S.-IV) WB-53 C 3045. for the Office of the Assistant Engineer- III, Central Mechanical Division, PHE. Dte. Under Bolpur Mechanical Division, P.H.E. Dte. | Assistant Engineer-III | Junior Engineer | ORD/001419/2023-2024 | 119/AE-III | 22/01/2024 | 23/04/2024 | RAJIB GHOSH | 0.44 | 0 | 0 | 0
8 | BIRBHUM | Labpur | Bolpur Mechanical | MASTALI PIPED WATER SUPPLY SCHEME | SM/16275 | New | Hiring of Car (B.S.-IV) WB-53 C 3045. for the Office of the Assistant Engineer- III, Central Mechanical Division, PHE. Dte. Under Bolpur Mechanical Division, P.H.E. Dte. | Assistant Engineer-III | Junior Engineer | ORD/001420/2023-2024 | 1132./AE-III | 12/09/2023 | 13/12/2023 | RAJIB GHOSH | 0.44 | 0 | 0 | 100
9 | BIRBHUM | Labpur | Bolpur Mechanical | MASTALI PIPED WATER SUPPLY SCHEME | SM/16275 | New | Hiring of Car (B.S.-IV) WB-53 C 3045. for the Office of the Assistant Engineer- III, Central Mechanical Division, PHE. Dte. Under Bolpur Mechanical Division, P.H.E. Dte. |  |  | ORD/001421/2023-2024 | 760/AE-III | 27/06/2023 | 27/09/2023 | RAJIB GHOSH | 0.44 | 0 | 0 | 100
10 | BIRBHUM | Labpur | Central Drilling | MASTALI PIPED WATER SUPPLY SCHEME | SM/16275 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21651.43 | 2.83 | 0.01