## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Rampurhat - II | Birbhum Division | Budhigram Piped Water Supply Scheme | SM/16762 | New | Continuation Work Order for Preparation & Submission of DPR for (Budhigram) Water Supply Scheme under Rampurhat-II Development Block. | AE | JE2 | ORD/000638/2022-2023 | 276/RSD | 18/08/2022 | 02/10/2022 | ECO CARE | 4.73 | 2.26 | 47.74 | 100
2 | BIRBHUM | Rampurhat - II | Birbhum Division | Budhigram Piped Water Supply Scheme | SM/16762 | New | Material Requisition To Resource Division |  |  | RTOR000084/2023-2024 | 1490/BHM | 25/04/2023 |  | Resource Division | 17.6 | 0 | 0 | 0
3 | BIRBHUM | Rampurhat - II | Bolpur Mechanical | Budhigram Piped Water Supply Scheme | SM/16762 | New | Providing Electro-mechanical accessories and others for Budhigram PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | Assistant Engineer-III | Junior Engineer | ORD/000474/2023-2024 | 2227/Bol.MD | 12/09/2023 | 11/11/2023 | SUNIL RABIDAS | 44.41 | 12.95 | 29.16 | 30
4 | BIRBHUM | Rampurhat - II | Bolpur Mechanical | Budhigram Piped Water Supply Scheme | SM/16762 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Budhigram PWSS under Rampurhat - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | Assistant Engineer-III | Junior Engineer | ORD/001233/2023-2024 | 519/BOL.MD | 14/03/2024 | 13/05/2024 | TAPAN ENTERPRISE | 7.61 | 0 | 0 | 0
Total | [13 empty] | 74.35 | 15.21 | 20.45