## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Labpur | Birbhum Division | LAYEKPUR PIPED WATER SUPPLY SCHEME | SM/18361 | New | Continuation work for "Preparation & Submission of Detail Project Report (DPR) for LAYEKPUR Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | AE | JE3 | ORD/000948/2022-2023 | 237/BSD | 17/06/2022 | 14/12/2022 | APEX ENGINEERING | 4.92 | 0 | 0 | 100
2 | BIRBHUM | Labpur | Birbhum Division | LAYEKPUR PIPED WATER SUPPLY SCHEME | SM/18361 | New | Continuation work for "Preparation & Submission of additional Detail Project Report (DPR) for LAYEKPUR Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | AE | JE3 | ORD/000953/2022-2023 | 300/BSD | 10/08/2022 | 08/11/2022 | APEX ENGINEERING | 2.46 | 0 | 0 | 100
3 | BIRBHUM | Labpur | Central Drilling | LAYEKPUR PIPED WATER SUPPLY SCHEME | SM/18361 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 17/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21347.15 | 0 | 0