## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Dubrajpur | Birbhum Division | Chinpai Piped Water Supply Scheme. | SM/18462 | New | Different works related to water supply scheme at CHINPAI, LOBA & PARATPUR and its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE | JE1 | ORD/000265/2023-2024 | 3476/BHM | 08/08/2023 | 04/05/2024 | B RAI CONSTRUCTION COMPANY | 2497.19 | 125.46 | 5.02 | 45
2 | BIRBHUM | Dubrajpur | Birbhum Division | Chinpai Piped Water Supply Scheme. | SM/18462 | New | Material Requisition To Resource Division |  |  | RTOR000070/2022-2023 | 1390/BHM | 24/04/2023 |  | Resource Division | 179.71 | 0 | 0 | 0
3 | BIRBHUM | Dubrajpur | Birbhum Division | Chinpai Piped Water Supply Scheme. | SM/18462 | New | Material Requisition To Resource Division |  |  | RTOR000186/2023-2024 | 3281/BHM | 27/07/2023 |  | Resource Division | 1.02 | 0 | 0 | 0
4 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Chinpai Piped Water Supply Scheme. | SM/18462 | New | Providing electro-mechanical accessories and others for Chinpai & Adjoining moujas water supply scheme under Bolpur Mechanical Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000383/2023-2024 | 1914/Bol.MD | 10/08/2023 | 04/08/2024 | M/S P.P ELECTRICALS | 106.93 | 28.45 | 26.6 | 50
5 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Chinpai Piped Water Supply Scheme. | SM/18462 | New | Supply and Delivery of Pump Starter, Diaphragm type Chlorinator dosing pump and Colum pipes at Chinpai and Adjoining moujas water supply scheme under Bolpur Mechanical Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/001314/2023-2024 | 707/Bol.MD | 27/03/2024 | 26/04/2024 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 7.99 | 3.99 | 50 | 100
Total | [13 empty] | 2792.85 | 157.9 | 5.65