## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Dubrajpur | Birbhum Division | Loba Piped Water Supply Scheme. | SM/18511 | New | Different works related to water supply scheme at CHINPAI, LOBA & PARATPUR and its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | AE | JE1 | ORD/000265/2023-2024 | 3476/BHM | 08/08/2023 | 04/05/2024 | B RAI CONSTRUCTION COMPANY | 2497.19 | 0 | 0 | 45
2 | BIRBHUM | Dubrajpur | Birbhum Division | Loba Piped Water Supply Scheme. | SM/18511 | New | Material Requisition To Resource Division |  |  | RTOR000072/2022-2023 | 1396/BHM | 24/04/2023 |  | Resource Division | 454.99 | 0 | 0 | 0
3 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Loba Piped Water Supply Scheme. | SM/18511 | New | Providing electro-mechanical accessories and others for Loba & Adjoining moujas water supply scheme under Bolpur Mechanical Division, PHE Dte | Assistant Engineer-III | Junior Engineer | ORD/000384/2023-2024 | 1915/Bol.MD | 10/08/2023 | 04/08/2024 | SINHA ELECTRICALS | 129.72 | 40.88 | 31.51 | 70
4 | BIRBHUM | Dubrajpur | Bolpur Mechanical | Loba Piped Water Supply Scheme. | SM/18511 | New | Supply & delivery of different electrical accessories at Loba Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. |  |  | ORD/000465/2024-2025 | 1310./AE-III | 28/08/2024 | 04/09/2024 | RMD TRADING | 2.78 | 0 | 0 | 0
Total | [13 empty] | 3084.69 | 40.88 | 1.33